## Sheet 1
Contract Handover Meeting Minutes
Date: |  | Project Manager:
Project No: |  | Site Foreman:
Project Name: |  | Director Responsible:
In Attendance
Job Opening Sheet Complete?
Has Order Been Received?
Has The PM Been Introduced To The Client?
Has A Thorough Review Of The Project Been Undertaken So That The PM Understands The Scheme In Full? Are There Any Actions To Be Taken?
Has A Review Of The Contract & Related Documents Been Completed? Is The Tender A True Reflection Of What Is Required? Are There Any Pitfalls That Need To Be Included In Costs? Has The Job Opening Sheet Been Reviewed & All Items Understood?
Has A Review Of The Contract Been Conducted By A Qualified Surveyor & All Contract Requirements Understood, Submitting of Variations, Recording Delays, Pitfalls & The Like? Ensure All Requirements & Risks Are Noted Below & Understood.
What Are The Design Requirements & Responsibilities / Procedure To Complete?
Have Tender Costs Been Reviewed For Adequacy & In Enough Detail To Complete A Project Analysis Sheet? Are There Any Shortfalls? Is A Schedule Of Rates Required?
Has The Proposal Document Been Reviewed & All Clarifications Understood?
Has The Project Manager Been Presented With All Of The Supplier / Sub-Contractor Quotations From Tender Stage So We Can Give Our Supply Chain The Opportunity As Thanks For Supporting At Tender Stage?
What Is The Method For Pricing Variations?
Do The PM / Site Foreman Have Suitable Experience To Deliver The Project? Are There Any Extra Measures Required?
Do Any Of The Team Involved Have Holidays That Fall During The Project? Are There Any Extra Measures Required?
Are There Any Known Health, Safety & Environmental Issues That Need Relaying To The PM?
Any Other Business
IP 02-04-36 Version 2