Internal Procedures

Section 3

Estimating, Purchasing

This document is uncontrolled when printed. Please refer to Sharepoint for the latest version.

IP-01-09-01-03

VERSION

DATE

AUTHOR

REVIEWED BY

APPROVED BY

NEXT REVIEW DATE

DOC REF

DATE

AUTHOR

REVIEWED BY

APPROVED BY

NEXT REVIEW DATE

Contents

INTRODUCTION	2

ESTIMATING	3

ESTIMATING FLOWCHART	29

PURCHASING	30

PURCHASING FLOWCHART	41

# INTRODUCTION

Our procedures exist for a reason. They protect our standards, our people and our reputation. At COMPANY NAME, following procedures isn’t about bureaucracy - it’s about delivering quality work with consistency and discipline. It reflects the pride we take in doing the job properly, the responsibility we have to our customers and colleagues and our commitment to continuous improvement.

Clear processes help us manage risk early, communicate effectively and ensure that no detail is overlooked. They create fairness, accountability and a shared way of working across the Group. Most importantly, they allow us to operate safely, professionally and profitably.

Everyone at COMPANY NAME is trusted to apply judgement within the framework we provide but that trust comes with the expectation that procedures are understood, followed and upheld. Doing so protects what makes us strong today and supports our progress for the future.

# ESTIMATING

1. Purpose

To ensure all tenders, quotations and estimates are reviewed, priced, checked, approved and submitted in a controlled and consistent manner.

The purpose of this procedure is to ensure that COMPANY NAME only tenders’ suitable opportunities, fully understands the technical and commercial risks, prices work accurately, protects margin, and provides clear handover information when a project is secured.

Estimating is not just a pricing exercise. It is a technical, commercial and risk management process. The estimator must understand what is being offered, what is excluded, what is assumed, what the risks are, and whether the works can be delivered safely, professionally and profitably.

2. Scope

This procedure applies to all estimating activity, including:

- New project tenders

- Design and build tenders

- Mechanical services tenders

- Electrical services tenders

- HVAC, ventilation, heating, chilled water, public health and controls tenders

- Small works quotations

- Planned maintenance quotations

- Reactive works quotations where a formal estimate is required

- Variations requiring estimating support

- Budget cost exercises

- Supplier and subcontractor quotation comparisons

- Tender handovers to Project Managers / Account Managers

This procedure covers the process from receipt of enquiry through to tender submission, post-tender clarification, order review and handover.

Please note that Section 3 controls procurement preparation and Section 6 controls commercial contract & payment administration.

Project Classification Definitions

Small Works

Small Works are projects that are generally:

- Valued at less than £30,000.

- Short duration in nature, typically completed within days or weeks rather than months

- Limited in scope and complexity

- Comprised of a single discipline or a small number of closely related work activities

- Delivered with minimal design, commercial and project management requirements

- Typically undertaken under a purchase order, quotation acceptance or simple contract arrangement

- Not subject to formal monthly applications for payment

- Not subject to retention, performance bonds, collateral warranties or other significant contractual obligations

- Low risk from a commercial, technical and programme perspective

Examples may include:

- Small electrical installations

- Minor mechanical modifications

- Equipment replacements

- Planned maintenance upgrades

- Small refurbishment works

- Reactive remedial works

- Controls modifications

- Minor HVAC alterations

Small Works Risk Assessment

The value of a project alone does not determine whether it should be managed as Small Works.

Where a project includes any of the following, it shall be reviewed by the responsible Director and may be managed under the full Project Management, Commercial and Design procedures regardless of value:

- Multiple work disciplines

- Significant design responsibility

- Complex phasing or programme constraints

- High-risk environments

- Retention provisions

- Applications for payment

- Liquidated damages

- Significant subcontract management

- Unusual contractual obligations

- Elevated health, safety or environmental risks

The responsible Director shall determine the appropriate management route where uncertainty exists.

3. Responsibilities

Estimator

- Review enquiry information

- Maintain the quotation register

- Set up the tender folder

- Review specifications, drawings, schedules and employer’s requirements

- Identify scope, exclusions, risks and qualifications

- Maintain communication with the Client throughout the tender period

- Prepare the estimate using approved estimating software where applicable

- Send enquiries to suppliers and subcontractors

- Complete take-offs and pricing build-ups

- Prepare the tender submission

- Ensure tender documentation is clear, professional and complete

- Support post-tender clarifications

- Complete tender handover information where an order is secured

Director / Business Unit Director

  - Decide whether to bid or decline where required

  - Confirm the enquiry aligns with company strategy, workload and risk appetite

  - Review and approve tenders above defined thresholds

  - Advise suitable sub-contractors/suppliers

  - Approve low-margin tenders

  - Review key risks before submission

  - Approve final tender position where required

Commercial Manager

  - Support credit insurance checks

  - Review commercial risk where required

  - Advise on payment terms, contract risk, retentions, damages and financial exposure

  - Support review of margin, preliminaries and commercial assumptions

Design Manager / Technical Lead

  - Assess the completeness of the tender package

  - Identify major or non-standard plant/equipment

  - Review design risk where applicable

  - Confirm whether the tender includes design responsibility

  - Review technical proposals, value engineering and design assumptions

  - Support technical clarifications and risk reviews

Project Manager / Account Manager

  - Support buildability, programme, access, logistics and delivery review where required

  - Attend tender settlement / handover where required

  - Confirm operational risks are understood before order acceptance

Procurement / Operations Support

  - Support supplier and subcontractor engagement where required

  - Assist with quotation returns, lead times and package comparisons

4. Procedure / Process

4.1 Receipt of Enquiry

All new enquiries must be reviewed promptly.

Upon receipt of an enquiry, the Estimator must:

- Confirm who the enquiry is from

- Confirm the client, end user and project location

- Confirm the tender return date and time

- Confirm the form of tender return required

- Identify whether the enquiry is competitive, negotiated, budgetary or for information only

- Identify the approximate value, if known

- Confirm the type of works and services involved

- Confirm whether COMPANY NAME has sufficient experience and resource to tender the works

A Director must be consulted where the enquiry is high value, strategically significant, unusual, design-heavy, commercially risky, or from a new client.

A Director is to be consulted to confirm whether the client and enquiry align with company aspirations and business plan. The client is then to be contacted within two working days to confirm whether the tender is being quoted or returned, if we are planning to tender the opportunity then the Bid / No Bid Review should be completed prior to telling the customer in case any issues arise.

4.2 Bid / No Bid Review

A Bid / No Bid decision must be completed before significant estimating time is committed. Document 02-04-55 – Bid, No Bid is to be used.

The review must consider:

- Client suitability

- End user suitability

- Credit insurance / financial risk

- Contract type

- Payment terms

- Retention requirements

- Liquidated damages

- Design responsibility

- Programme risk

- Tender return date

- Resource availability

- Technical capability

- Location and logistics

- Existing workload

- Strategic value

- Margin opportunity

- Health, safety and environmental risk

- Whether the opportunity aligns with COMPANY NAME business objectives

The tender should be declined where the risk, resource requirement or commercial exposure is not acceptable unless a Director confirms otherwise.

Where credit insurance is insufficient or unavailable, the relevant Director must decide whether the risk/reward position justifies proceeding.

4.3 Quotation Register and Tender Number

Once the enquiry is accepted for tender, the Estimator must:

- Enter the enquiry onto the Quotation Register located in folder 03 on Sharepoint

- Take the next quotation number

- Record client, project, value, return date, estimator and status

- Record bid / no bid decision

- Record any Director approvals or key comments

The Quotation Register is the primary control document for estimating workload and tender status.

4.4 Tender Folder Setup

A tender folder must be created for every accepted enquiry.

The tender folders located in folder 03 must be organised so that another competent person can understand the enquiry, pricing basis and tender submission without needing verbal explanation.

The folder is to be laid out as per document 02-01-21 Quotation Index Sheet

The folder should include, as applicable:

- Enquiry email

- Tender invitation

- Drawings

- Specifications

- Employer’s Requirements

- Contract Sum Analysis / pricing document

- Schedules

- Site information

- Existing services information

- Addendums

- Clarifications

- Supplier quotations

- Subcontractor quotations

- Take-off information

- Estimate file

- Tender review notes

- Risk register / risk notes

- Qualifications and exclusions

- Tender submission

- Post-tender correspondence

- Final submitted PDF

All tender information must be saved in the tender folder. Information should not remain only in personal email inboxes.

4.5 Initial Tender Review

Before pricing begins, the Estimator must complete an initial review of the tender information.

The review must identify:

- Tender return date

- Scope of works

- Services included

- Services excluded

- Design responsibility

- Construction programme

- Phasing requirements

- Site constraints

- Access restrictions

- Working hours

- Out-of-hours requirements

- Preliminaries requirements

- Welfare or site setup requirements

- Testing and commissioning requirements

- O&M / handover requirements

- Warranty requirements

- Client-specific requirements

- Any obvious gaps, contradictions or risks

The Estimator must identify whether the tender is:

- Fully designed

- Contractor designed

- Design and build

- Performance specified

- Budget only

- Based on incomplete information

- Whether the tender information is sufficient to price accurately

- Whether design resource is required to assist with outline design or technical development

- Whether the Contract Sum Analysis / pricing schedule has been located and reviewed

- How the tender should be broken down for pricing purposes

Where information is incomplete, the Estimator must either raise a clarification or include a clear qualification in the tender return.

The Estimator must assess whether there is enough information to price the tender properly. Where the information is incomplete, unclear, performance-based, or requires design input, this must be identified at the earliest opportunity.

Where design support is required, the Estimator must notify the Design Manager / Design Department as soon as possible so that suitable resource can be allocated to assist with outline design, technical assumptions, equipment selections or pricing information.

At this stage, the Estimator should also locate and review the Contract Sum Analysis, pricing schedule or tender breakdown. This should be used to help structure the estimate and identify the sections, packages and work elements that need to be priced.

4.6 Technical Scope Review

The estimate must be built around the technical scope of the engineering services.

The Estimator must review, where applicable:

Mechanical

  - Heating systems

  - Chilled water systems

  - Ventilation systems

  - Air-conditioning systems

  - Domestic water services

  - Steam & Condensate services

  - Specialist Gases

  - Heavy plant

  - Gas services

  - Above-ground drainage

  - Pumps and pressurisation

  - Plantrooms

  - Insulation

  - Bracketing and supports

  - Commissioning and balancing

  - Builders work associated with mechanical services

  - Plant access and replacement routes

Electrical

  - LV distribution

  - High voltage electrical works

  - Lighting and emergency lighting

  - Small power

  - Containment

  - Fire alarm interfaces

  - Data / structured cabling where included

  - Controls wiring

  - Mechanical power supplies

  - Earthing and bonding

  - Testing and certification

  - Temporary supplies where required

Controls / BMS

  - Controls philosophy

  - BMS head-end requirements

  - Points schedules

  - Control panels

  - Field wiring

  - Sensors and actuators

  - Integration with third-party systems

  - Graphics

  - Commissioning and witnessing

  - Remote monitoring requirements

Specialist / Associated Works

  - Builders work/Civils/Structural

  - Fire stopping

  - Access panels

  - Craneage and lifting

  - Scaffolding and access equipment

  - Thermal insulation

  - Water treatment

  - Commissioning management

  - Validation

  - Specialist testing

  - Demonstration and training

  - O&M information

The Estimator must not assume items are excluded simply because they are not obvious. If the specification, drawings or employer’s requirements imply a responsibility, it must be priced, clarified or qualified.

4.7 Specification Review

The specification must be read in full before the estimate is finalised.

The review must identify:

  - Material requirements

  - Manufacturer requirements

  - Installation standards

  - Testing requirements

  - Commissioning requirements

  - Documentation requirements

  - Warranty requirements

  - Sample / mock-up requirements

  - Inspection and witnessing requirements

  - Quality requirements

  - Fire stopping requirements

  - Acoustic requirements

  - Insulation requirements

  - Trace heating requirements

  - Controls requirements

  - Labelling requirements

  - O&M requirements

  - Maintenance requirements during defects period

The Estimator must pay particular attention to clauses that create hidden cost or risk, including:

  - Out-of-hours working

  - Restricted working areas

  - Security clearance

  - Specialist access

  - Phased handovers

  - Temporary works

  - Design responsibility

  - Coordination responsibility

  - BIM / Revit requirements

  - Lead consultant duties

  - Responsibility for surveys

  - Responsibility for existing services

  - Witness testing

  - Extended warranties

  - Performance damages

  - Liquidated damages

At the first reading of the specification the initial headings of each service / product type should be established to assist with the layout of the estimating software layout, so no items are missed.

4.8 Drawing Review

All drawings must be reviewed before finalising the estimate.

The Estimator must check:

  - Drawing revisions

  - Drawing scale

  - Drawing status

  - Architectural constraints

  - Plant locations

  - Riser routes

  - Ceiling void constraints

  - External routes

  - Existing services

  - Builder’s work requirements

  - Access and maintenance space

  - Plant replacement routes

  - Coordination risks

  - Drawing/specification discrepancies

Where drawings and specifications conflict, the Estimator must raise a clarification or include a qualification in the tender submission.

4.9 Tender Clarifications and RFIs

Clarifications must be raised where information is missing, contradictory or commercially significant using document 02-01-07 RFI Template.

Clarifications may relate to:

  - Scope gaps

  - Drawing/specification conflicts

  - Design responsibility

  - Builders work responsibility

  - Fire stopping responsibility

  - Access responsibility

  - Controls responsibility

  - Commissioning responsibility

  - BMS integration

  - Phasing

  - Programme

  - Preliminaries

  - Retention

  - Payment terms

  - Contract conditions

  - Liquidated damages

All clarifications issued and responses received must be saved in the tender folder.

Where no response is received before tender submission, the tender must include appropriate assumptions, qualifications or exclusions.

4.10 Estimating Software Setup

Where suitable, estimating software should be used as the primary method of pricing.

Manual estimating may be used for small works, early budgets or simple quotations, but the estimate must still be structured, auditable and clear.

The estimate must be set out to align with:

  - Client pricing schedule

  - Contract Sum Analysis

  - Specification sections

  - Service type

  - Building area

  - Floor level

  - Work package

  - Or another logical breakdown agreed by the Estimator and Director

The estimate must allow costs to be understood clearly during tender review and project handover.

4.11 Take-Offs

Take-offs must be completed by service, system, area or package.

Before completing take-offs, the Estimator must check:

  - Latest drawings are being used

  - Scale is correct

  - Specification has been reviewed

  - Drawing notes have been checked

  - Relevant schedules have been reviewed

  - Any assumptions are recorded

Take-offs should include, where applicable:

  - Pipework

  - Ductwork

  - Cable containment

  - Cable lengths

  - Equipment quantities

  - Valves and accessories

  - Grilles, diffusers and louvres

  - Supports and bracketry

  - Insulation

  - Controls devices

  - Plant items

  - Builders work items

  - Fire stopping items

  - Testing and commissioning items

The take-off must be sufficiently clear for another competent person to review.

4.12 Supplier and Subcontractor Enquiries

Supplier and subcontractor enquiries must be issued early enough to obtain competitive and reliable returns.

All supplier/subcontractor packages are to be reviewed early, with at least three prices obtained during estimating wherever possible.

The Estimator must:

  - Identify all supplier packages

  - Identify all subcontractor packages

  - Issue clear enquiry documents

  - Include relevant drawings, specifications and schedules

  - State return date

  - State project location

  - State programme requirements where known

  - State whether design is required

  - State whether attendance, access or commissioning is required

  - Record enquiries issued

  - Save all returns in the tender folder

Supplier enquiries may use:

  - 02-04-21 – Supplier Quotation Request

Subcontractor enquiries may use:

  - 02-04-33 – Sub-Contract Tender Enquiry

Where fewer than three prices are obtained, the reason must be recorded.

Where supplier or subcontractor quotations are obtained during the estimating stage, they are used to support the tender price only. Before any order is placed, quotations must be reviewed, confirmed as current and progressed in accordance with the Purchasing Procedure and, where relevant, the Commercial & Accounting Procedure.

4.13 Supplier and Subcontractor Quotation Review

Returned quotations must be reviewed properly before being included in the estimate.

The Estimator must check:

  - Scope is complete

  - Exclusions are acceptable

  - Qualifications are understood

  - Delivery periods are acceptable

  - Specification compliance

  - Manufacturer compliance

  - Technical compliance

  - Commissioning included where required

  - Controls integration included where required

  - Delivery, carriage and offloading included

  - Warranty requirements included

  - Any design responsibility is clear

  - Any attendances required from COMPANY NAME are understood

Lowest price must not be used automatically. The selected quotation must represent the best combination of compliance, value, risk and deliverability.

Any major quotation exclusions or assumptions must be either:

  - Costed elsewhere in the estimate

  - Clarified with the supplier/subcontractor

  - Included as a tender qualification

  - Reviewed with a Director

4.14 Labour, Productivity and Installation Risk

Labour must be assessed realistically.

The Estimator must consider:

  - Site location

  - Working hours

  - Tender Issue Programme

  - Access restrictions

  - Working at height

  - Confined spaces

  - Security procedures

  - Phasing

  - Congested areas

  - Live environment

  - Existing services

  - Plant movement

  - Logistics

  - Productivity constraints

  - Supervision requirements

  - Testing and commissioning periods

  - Snagging and completion requirements

Where labour allowances are based on standard outputs, they must be adjusted for project-specific conditions.

4.15 Preliminaries and Site-Specific Costs

Preliminaries must be reviewed and priced based on the project requirements.

The estimate must consider:

  - Project management

  - Site management

  - Supervision

  - Site setup

  - Welfare

  - Storage

  - Small tools

  - Plant and access equipment

  - Scaffolding / towers / MEWPs

  - Craneage and lifting

  - Waste management

  - Deliveries and logistics

  - Parking

  - Permits

  - Security clearance

  - Site inductions

  - Temporary works

  - Temporary supplies

  - Testing equipment

  - Commissioning management

  - O&M production

  - Handover attendance

  - Travel and accommodation

  - Out-of-hours working

Preliminaries should not be guessed or reduced simply to improve tender competitiveness without Director approval.

4.16 Design, Coordination and Technical Risk

Where COMPANY NAME has design responsibility, design costs and risk must be included.

The Estimator, in conjunction with the Design Manager, must consider:

  - Design management

  - Design engineering hours

  - CAD / Revit / BIM requirements

  - Coordination meetings

  - Design workshops

  - Technical submissions

  - Calculations

  - Schedules

  - Design risk assessments

  - Design changes

  - External consultants

  - Thermal modelling / BRUKL / specialist reports where applicable

  - BIM Execution Plan requirements

  - As-fitted drawings

The Design Procedure already places importance on design deliverables, calculations, technical submissions, design risk assessment, maintainability and design handover. Estimating must therefore allow sufficient cost and time for these items where they form part of the tender scope.

4.17 Commissioning, Handover and O&M Requirements

Commissioning and handover must be priced and planned from tender stage.

The Estimator must consider:

  - Commissioning engineers

  - Balancing

  - Water treatment

  - Chlorination

  - Pressure testing

  - Electrical testing

  - Fire damper testing

  - Controls commissioning

  - BMS commissioning

  - Seasonal commissioning

  - Witness testing

  - Demonstrations

  - Client training

  - O&M manuals

  - Record drawings

  - Asset schedules

  - Warranty documents

  - Handover meetings

  - Close-out documentation

Where the specification requires detailed commissioning or validation, this must be included in the estimate or clearly qualified.

4.18 Health, Safety and Environmental Requirements

The tender review must consider health, safety and environmental implications.

The Estimator must identify cost and risk associated with:

  - Working at height

  - Hot works

  - Confined spaces

  - Live electrical environments

  - Existing services

  - Asbestos information

  - Lifting operations

  - Noise and vibration

  - Dust and waste

  - Hazardous substances

  - Refrigerants

  - Gas works

  - High-risk permits

  - Waste management

  - Site-specific welfare or safety requirements

Where subcontractors are likely to be required, estimating must take account of the need for approved, competent and insured subcontractors. The subcontractor procedure requires subcontractors to be formally approved, competence verified, and the Subcontractor H&S Register used as the primary control before works commence.

4.19 Commercial Risk Review

The Estimator must review commercial risk before finalising the tender.

This must include:

  - Payment terms

  - Retention

  - Liquidated damages

  - Parent company guarantees

  - Performance bonds

  - Design liability

  - Collateral warranties

  - Programme damages

  - Delay risk

  - Inflation risk

  - Material price volatility

  - Currency risk where applicable

  - Long lead items

  - Client credit risk

  - Main contractor risk

  - Contract amendments

Commercial risks must be referred to the Commercial Manager and/or Director where they are unusual, high value or outside normal company risk appetite.

4.20 Tender Qualifications and Exclusions

All tender qualifications and exclusions must be clear, specific and professional.

They must not be vague or hidden.

Qualifications may include:

  - Basis of design

  - Drawing revision basis

  - Specification basis

  - Programme assumptions

  - Working hours

  - Exclusions

  - Attendances required by others

  - Design exclusions

  - Builders work exclusions

  - Fire stopping exclusions

  - Controls exclusions

  - BMS exclusions

  - Testing exclusions

  - Commissioning exclusions

  - O&M assumptions

  - Payment terms

  - Validity period

  - Lead time assumptions

Where an item is excluded because it is not clearly defined, the tender should explain the basis of exclusion and offer to price if further information is provided.

4.21 Margin and Mark-Up

Mark-up must be applied in accordance with company requirements.

To align with existing commercial practice, mark-ups should be applied on sell, not on cost, unless specifically agreed otherwise.

The Estimator must not reduce margin below expected levels without Director approval.

The tender review must consider:

  - Project risk

  - Client risk

  - Programme risk

  - Technical complexity

  - Level of design responsibility

  - Competition

  - Strategic value

  - Cashflow

  - Current workload

  - Business unit margin requirements

4.22 Tender Review and Approval

Before submission, tenders must be reviewed in proportion to value and risk.

Minimum review requirements:

  - Tenders up to £20,000 with margins pre-agreed with a Director may be reviewed and submitted by the Estimator, unless high risk

  - Tenders up to £100,000 should be reviewed by another competent person, manager or Director and can again be submitted at pre- agreed margins

  - Tenders over £100,000 must be reviewed with a Director

  - Any tender with margin below company target must be approved by a Director

  - Any tender with significant design, contract, programme, credit or delivery risk must be approved by a Director regardless of value

The review must confirm:

  - Scope is understood

  - Estimate is complete

  - Supplier/subcontractor quotations are reviewed

  - Labour allowances are reasonable

  - Preliminaries are included

  - Technical risks are identified

  - Commercial risks are identified

  - Qualifications are clear

  - Margin is appropriate

  - Submission is professional and complete

4.23 Tender Submission

Tender submissions must be professional, clear and complete and as per document 02-11-01 – Proposal Template.

The submission should include:

  - Covering email or letter

  - Tender proposal

  - Completed pricing schedule / CSA where required

  - Qualifications and exclusions

  - Programme assumptions

  - Validity period

  - Payment assumptions where applicable

  - Any required forms or declarations

  - Relevant supporting technical information where appropriate

All tender submissions must be saved as PDF before issue.

The final submitted tender, including covering email and attachments, must be saved in the tender folder.

4.24 Post-Tender Clarifications

All post-tender clarifications must be controlled.

The Estimator must:

  - Save all clarification correspondence

  - Review requested changes carefully

  - Confirm whether clarification affects price, programme or risk

  - Update the estimate where required

  - Obtain Director approval where changes affect margin or risk

  - Clearly identify revised submissions

  - Save final revised submissions in the tender folder

No verbal change to scope or price should be relied upon unless confirmed in writing.

4.25 Negotiation and Value Engineering

Value engineering may be offered where it provides benefit to the client and COMPANY NAME.

Value engineering must be:

  - Technically suitable

  - Clearly described

  - Properly costed

  - Approved internally

  - Separated from the base tender where appropriate

  - Supported by clear assumptions and exclusions

The Estimator must not offer value engineering that compromises safety, quality, compliance, maintainability or COMPANY NAME standards.

4.26 Order Review Before Acceptance

Before accepting any order, the tender and proposed order must be reviewed.

The review must confirm:

  - Order matches tender submission

  - Scope matches priced scope

  - Qualifications have been included or accepted

  - Contract terms are acceptable

  - Payment terms are acceptable

  - Retentions are acceptable

  - Programme is achievable

  - Design responsibility is understood

  - Credit insurance / client risk is acceptable

  - Resources are available

  - Any changes from tender are priced or agreed

The Director is to be consulted before accepting any order to confirm resource, credit insurance and suitability.

4.27 Tender Handover

Where a tender is successful, a formal handover must be completed.

The handover must include:

  - Tender submission

  - Final agreed price

  - Cost build-up

  - Margin

  - Supplier quotations

  - Subcontractor quotations

  - Labour allowances

  - Preliminaries

  - Assumptions

  - Qualifications

  - Exclusions

  - Risks and opportunities

  - Design responsibility

  - Programme assumptions

  - Procurement lead times

  - Long lead items

  - H&S / environmental risks

  - Client communications

  - Post-tender clarifications

  - Any verbal agreements confirmed in writing

The Estimator is to support the Project Management team in completing the Project Analysis Sheet as and where required so the Project Manager understands cost allowances and margin.

The Project Management Procedure requires the project team to review the tender, contract documents, drawings, specifications, quotations and costs during handover, and to confirm that the tender is a true reflection of what is required. The estimating handover must therefore be detailed enough to support that project review.

5. Compliance / Key Rules

  - Every accepted enquiry must be logged on the Quotation Register

  - A tender folder must be created for every accepted enquiry

  - A Bid / No Bid review must be completed before significant estimating work is undertake

  - Specifications and drawings must be reviewed before tender submission

  - Scope gaps, contradictions and assumptions must be clarified or qualified

  - Supplier and subcontractor enquiries must be issued early

  - At least 3 quotations should be obtained for supplier and subcontract packages wherever practical

  - Returned quotations must be technically and commercially reviewed

  - Estimates must include preliminaries, commissioning, handover and design costs where applicable

  - Commercial risks must be referred to the Commercial Manager and/or Director

  - Low-margin or high-risk tenders require Director approval

  - Tenders over £100,000 require Director review

  - Final submissions must be saved as PDF

  - No tender should be submitted late without the client being informed in advance

  - Successful tenders must be handed over formally before project delivery begins

6. Records / Documentation

  - Tender Folder

  - Proposal Document

  - Estimating Software File

  - Generic Take-Off Sheet

- 02-01-07 RFI Template

- 02-01-21 Quotation Index Sheet

- 02-04-02 - Project Analysis Sheet

- 02-04-11 – Quotation Register

- 02-04-20 – Purchasing Sheet

- 02-04-21 – Supplier Quotation Request

- 02-04-33 – Sub-Contract Tender Enquiry

- 02-04-55 – Bid, No Bid

- 02-11-01 – Proposal Template

- Supplier quotations

- Subcontractor quotations

- Clarification log / emails

- Tender review notes

- Tender submission PDF

- Post-tender clarification records

- Tender handover notes

7. Monitoring & Review

Estimating activity shall be monitored through:

  - Quotation Register review

  - Tender review meetings

  - Director tender approvals

  - Post-tender feedback

  - Tender win/loss review

  - Project handover feedback

  - Project commercial performance review

  - Lessons learned following project completion

Where a project performs materially different from the estimate, the reason should be reviewed and fed back into future estimating practice.

This may include:

  - Missed scope

  - Incorrect labour allowance

  - Incorrect preliminaries

  - Poor supplier/subcontractor quote review

  - Design responsibility not allowed for

  - Programme risk not understood

  - Procurement risk not identified

  - Tender qualifications not carried through into contract

  - Client changes not captured

8. References

  - Section 3 – Purchasing Procedure

  - Section 4 – Design & Project Management Procedure

  - Section 6 – Commercial & Accounting Procedure

  - Section 7 – Environmental, Health & Safety Procedure

  - Section 8 – Training Procedure

  - Section 9 – Company Engineers & Subcontractors Procedure

  - COMPANY NAME Playbook

  - Quotation Register

  - Subcontractor H&S Register

9. Key Principles

  - We only tender work we understand and can deliver

  - We price engineering properly, not hopefully

  - Scope, risk and responsibility must be clear before submission

  - The cheapest quote is not always the right quote

  - Design, commissioning, handover and preliminaries must not be forgotten

  - Commercial risk must be identified early

  - Tender submissions must be professional and auditable

  - Handover must allow the Project Manager to deliver what was sold

  - Estimating must protect quality, margin, reputation and customer relationships

## ESTIMATING FLOWCHART

1.       Receive & Log Enquiry

- Appoint estimator with suitable experience for the type, value and complexity of enquiry

- Review client, project, location, tender return date and high-level scope

- Complete quotation register and allocate quotation number

- Confirm whether the enquiry is aligned with company strategy, workload and capability

- Consult Director where required

- Take Offs & Build Estimate

- Complete take-offs by service, system, area or package

- Input quantities into estimating software

- Price materials, labour, subcontractors, plant, access, preliminaries, design, commissioning, O&M and handover requirements

- Include allowances for site conditions, logistics, phasing, access restrictions and programme requirements

- Record assumptions clearly

- Send Out Supplier & Subcontractor Enquiries

- List all supplier and subcontractor packages requiring quotations

- Issue enquiries at the earliest opportunity to allow sufficient time for returns

- Obtain 3 quotations where practical

- Ensure enquiries include relevant drawings, specifications, schedules, scope notes, return date and programme requirements

- Save all enquiries and quotation returns in the tender folder

- Specification & Drawing Review

- Read the specification and tender documents in full

- Review drawings, schedules and employer’s requirements

- Check drawing revisions, scale, scope, service routes, plant locations, access, logistics and coordination risks

- Identify technical risks, design requirements, commissioning requirements, handover requirements and any gaps in information

- Prepare Estimating Software / Pricing Structure

- Create estimate within the enquiry folder

- Set up the estimate to match the client’s Contract Sum Analysis where provided

- Where no Contract Sum Analysis is provided, set up the estimate by specification section, service type, area, floor or work package

- Ensure all headings are clear so that no major scope items are missed

3.        Initial Tender Review

- Review the enquiry information and identify the scope of works

- Check whether there is enough information to price the tender properly

- Identify whether design resource is required and notify the Design Manager / Design Department at the earliest opportunity

- Locate and review the Contract Sum Analysis, pricing schedule or tender breakdown

- Use the Contract Sum Analysis to start forming the pricing structure and work package breakdown

- Identify key risks, missing information, assumptions, clarifications and exclusions

- Create Tender Folder & Organise Information

- Create new quotation / tender folder

- Save all enquiry information in a clear and structured manner

- Upload drawings, specifications, schedules, employer’s requirements, addendums and correspondence

- Start proposal document and include project title, customer details, quote number and return requirements

The estimating flowchart is provided as a condensed visual summary of the estimating process. It is intended to support understanding and day-to-day use of this procedure but does not replace the full written procedure.

All personnel must ensure they understand and follow the full Estimating Procedure.

- 02-04-02 - Project Analysis Sheet

- Order Review & Tender Handover

- Where an order is received, review the order against the tender submission

- Confirm scope, price, qualifications, exclusions, terms, programme, payment terms and risks

- Complete a formal handover to the Project Manager / Account Manager

- Include estimate build-up, supplier/subcontractor quotations, assumptions, risks, opportunities, design requirements and procurement lead times

- Post Tender Clarifications

- Manage any post-tender queries, clarifications, value engineering or revised prices

- Record all correspondence and update the estimate where required

- Seek Director approval where changes affect margin, risk, scope or programme

- Save all revised submissions in the tender folder

- Submit Tender

- Issue tender to the client in the required format before the deadline

- Save the issued email, final PDF and all attachments in the tender folder

- Update quotation register with submission date, value and status

- Tender Review & Approval

- Review tender internally prior to submission

- Check scope, costs, labour, preliminaries, design allowance, commissioning, handover, margin, risk, qualifications and exclusions

- Director review is required for high-value, high-risk or low-margin tenders

- Commercial Manager / Design Manager / Technical Lead input should be obtained where required

- 02-11-01 – Proposal Template

- Prepare Tender Submission

- Prepare proposal document and tender return

- Include price, scope, qualifications, exclusions, assumptions, validity period and programme assumptions

- Ensure tender breakdown matches the Contract Sum Analysis or client pricing schedule where required

- Convert final submission to PDF before issue

- Save final tender submission and covering email in the tender folder

- 02-04-20 – Purchasing Sheet

- Review Supplier & Subcontractor Quotations

- Review quotation returns for scope, compliance, exclusions, attendances, lead times and technical suitability

- Do not select on price alone; check best value, compliance and risk

- Identify any gaps that need pricing elsewhere or qualifying in the tender

- Confirm any major exclusions or risks with the Director / Technical Lead where required

- 02-04-21 – Supplier Quotation Request

- 02-04-33 – Sub-Contract Tender Enquiry

- 02-04-20 – Purchasing Sheet

- 02-01-07 RFI Template

- 02-01-21 Quotation Index Sheet

- 02-11-01 – Proposal Template

- 02-04-11 – Quotation Register

- 02-04-55 – Bid, No Bid

# PURCHASING

1. Purpose

To ensure all purchasing activities are controlled, commercially managed, properly approved, and recorded in a consistent manner.

This procedure is intended to ensure that COMPANY NAME obtains competitive value, uses approved and competent suppliers and subcontractors, maintains clear records, and prevents commitments being made without the correct authority.

2. Scope

This procedure applies to all purchasing activity across COMPANY NAME, including:

- Supplier purchases

- Project material purchases

- Plant, equipment and hire purchases

- Labour only subcontractors

- Bona-fide subcontractors

- Project and small works procurement

- Maintenance procurement

- Subcontract orders

- Purchase orders raised through the accounts system

This procedure does not replace the requirements of the project management, commercial, accounts, subcontractor or health and safety procedures. Where purchasing relates to project works, the purchasing process must be followed alongside the relevant project procedure.

3. Responsibilities

Project Managers / Account Managers

- Identify purchasing requirements

- Obtain quotations

- Check supplier and subcontractor suitability

- Raise purchase orders

- Ensure orders are correctly coded to the relevant project

- Save purchase orders and supporting quotations in the correct project file

- Monitor deliveries and supplier performance

- Ensure costs are updated on the Project Analysis Sheet where applicable

Directors

- Approve supplier orders over £25,000

- Approve unapproved suppliers or subcontractors where required

- Approve all bona-fide subcontractors before use

- Approve subcontract orders over £25,000

- Approve deviations from standard payment terms

Accounts Manager

- Process supplier and subcontractor accounts

- Confirm supplier payment terms

- Match invoices to purchase orders

- Ensure invoices are approved before entry or payment

- Prevent payments being made where required documentation is missing

Health & Safety Manager

- Maintain the Subcontractor H&S Register

- Confirm subcontractor approval status where required

- Ensure subcontractor insurances, competence and RAMS requirements are controlled in accordance with the subcontractor procedure

Commercial Manager

- Review purchasing information where required for cost control, cashflow and project reporting

- Support purchasing decisions where there is commercial risk, payment term risk or cost exposure

4. Procedure / Process

Relationship with Commercial & Accounting Procedure

This Purchasing Procedure controls the procurement stage up to and including supplier selection, quotation comparison, purchase order / subcontract order approval and order issue. It must be read alongside the Commercial & Accounting Procedure, which provides the detailed controls for invoice processing, subcontractor applications, payment certificates, retentions, final account statements, payment authorisation, accounting system entries and commercial reporting.

Where this procedure refers to purchase orders, subcontract applications, invoice approval, payment terms, payment certificates, retentions or final payments, the Commercial & Accounting Procedure must be followed for the detailed process requirements.

4.1 General Purchasing Control

All purchases must be supported by an official purchase order.

Purchase orders must be raised before goods, services or subcontract works are instructed, except where emergency works make this impractical. Where an emergency purchase is made, a purchase order must be raised as soon as possible afterwards and the reason must be recorded.

All purchase orders must include:

- Supplier or subcontractor name

- Project or cost code

- Clear description of goods or services – for suppliers is must reference a attached schedule of materials / equipment, any orders for hire equipment must list the equipment being hired, all sub-contractor orders must reference section 6

- Agreed price

- Delivery address or site location

- Payment terms where applicable

- Any relevant references to quotations, drawings, specifications or terms and conditions

A copy of the purchase order must be saved in the relevant project, contract or department file.

4.2 Quotation Requirements

At least 3 quotations must be obtained for supplier purchases wherever practical.

At least 3 quotations must also be obtained for subcontract packages wherever practical.

Where 3 quotations cannot be obtained, the reason must be recorded. Examples may include:

- Specialist supplier

- Emergency requirement

- Client-nominated supplier

- Continuity with existing equipment or systems

- Lack of available market alternatives

- Programme-critical requirement

The decision must still demonstrate commercial judgement and, where there is any doubt, must be referred to a Director.

4.3 Supplier Purchases

Where purchasing is being completed at the outset of a project, supplier package values should be recorded on:

- 02-04-20 - Purchasing Sheet

The Purchasing Sheet should be presented to the relevant Director for approval prior to orders being placed where the purchase package is significant or forms part of the initial project procurement strategy.

When requesting quotations from suppliers, the following form may be used:

- 02-04-21 - Supplier Quotation Request

Supplier orders under £25,000 may be raised by the Project Manager responsible for the project.

Supplier orders of £25,000 and above require Director approval before the order is placed.

Approval shall be demonstrated by:

- Project Manager / Account Manager signing the purchase order

- Director countersigning the purchase order

- Signed purchase order being saved in the relevant file

4.4 Supplier Payment Terms

Payment terms must be agreed before placing an order with a new supplier.

As a general rule:

Supplier orders under £25,000 should be on payment terms no sooner than 45 days end of month

Supplier orders of £25,000 and above should be on payment terms of 60 days end of month where possible

Any deviation from the above must be approved by a Director

Payment terms must be communicated to Accounts so the supplier record can be correctly maintained.

4.5 Delivery and Goods Receipt

The person responsible for the purchase must ensure:

- Delivery arrangements are agreed

- Delivery dates are suitable for the programme

- Delivery notes are checked against the purchase order

- Any shortages, damages or incorrect deliveries are reported immediately

- Delivery notes are saved in the relevant project or site file where applicable

Where deliveries affect programme or client commitments, delays must be communicated to the Project Manager / Account Manager immediately.

4.6 Labour Only Subcontractors

Labour only subcontractors are single operatives working under COMPANY NAME control and using timesheets.

Labour only subcontractors must not be treated as bona-fide subcontractors.

Before using a labour only subcontractor, the Project Manager / Account Manager must check the Subcontractor H&S Register to confirm:

- They are approved for use

- Required information is complete

- Their competence has been verified

- Relevant training certificates or trade cards have been obtained where applicable

Where there is a requirement to use an unapproved labour only subcontractor, Director approval must be obtained before they start work.

Labour only subcontractors must use:

- 02-04-19 - Timesheet

They do not need to provide invoices to support their timesheets. Any expenses must be clearly broken down and supported by receipts where applicable.

4.7 Bona-Fide Subcontractors

Bona-fide subcontractors are independent subcontractors who operate under their own control and may provide labour, supervision, materials, plant or design.

Before placing an order with a bona-fide subcontractor, the Project Manager / Account Manager must check the Subcontractor H&S Register to confirm:

- The subcontractor is approved

- Director approval has been obtained

- The subcontractor questionnaire has been completed

- Insurances are valid and in date

- Competence has been verified

- The subcontractor is suitable for the works being procured

A bona-fide subcontractor must not commence work unless the requirements of the Company Engineers & Subcontractors procedure have been satisfied.

Where there is a requirement to use an unapproved bona-fide subcontractor, Director approval must be obtained before any commitment is made.

4.8 Bona-Fide Subcontractor Quotations and Purchasing Sheet

At least 3 quotations must be obtained for all bona-fide subcontract packages wherever practical.

When subcontract packages are being procured at the outset of a project, the package values should be recorded on:

- 02-04-20 - Purchasing Sheet

The Purchasing Sheet should be presented to the relevant Director for approval prior to orders being placed.

4.9 Bona-Fide Subcontractor Approval Levels

Subcontract package values under £25,000 may be purchased by the Project Manager / Account Manager, provided:

- The subcontractor is approved

- There is no subcontractor design involved

- The correct purchase order is raised

- The order references COMPANY NAME subcontractor terms and conditions

- The order is saved in the project file

Subcontract package values of £25,000 and above require Director approval.

Any subcontract package involving subcontractor design requires Director approval regardless of value.

4.10 Bona-Fide Subcontractor Payment Terms

Payment terms with bona-fide subcontractors must be a minimum of 45 days.

These terms must be confirmed prior to placing any subcontract order.

Any deviation from the minimum 45-day requirement must be approved by a Director.

4.11 Retention Requirements

Retentions held by COMPANY NAME against bona-fide subcontractors must normally be:

- 5% retention

- Reducing to 2.5% on practical completion

Where the customer is holding a higher retention against COMPANY NAME, the retention held against the subcontractor must be increased to match the customer's retention where appropriate.

Where the subcontract order value is less than £25,000 nett, retention held by COMPANY NAME may be nil.

4.12 Applications for Payment

Bona-fide subcontractors must use applications for payment unless:

- The order value is less than £25,000 nett; and

- COMPANY NAME is not withholding retention; and

- The subcontractor has been permitted to invoice instead

Where applications for payment are required, the process must align with the commercial and accounts procedures.

4.13 Bona-Fide Subcontract Order Documents

4.13.1 Under £25,000 with no design

- Purchase order may be raised directly from the accounts system

- Purchase order must reference COMPANY NAME subcontractor terms and conditions

- Purchase order must be saved in the project file

4.13.2 £25,000 to £100,000

- Use 02-04-31a - Subcontractor Purchase Order Form

- Director approval required – by initialling the PDF of the order

- Subcontractor must sign and return the order before commencing works

- Signed order must be saved in the project file

4.13.3 Over £100,000

- Use 02-04-31b - Subcontractor Purchase Order Form

- Director approval required - by initialling the PDF of the order

- Subcontractor must sign and return the order before commencing works

- Pre-start meeting must be completed using 02-04-32 - Subcontractor Pre-Start Meeting

- Signed order and pre-start meeting record must be saved in the project file

4.14 Control of Subcontract Orders Issued by Email

Where a subcontract order is issued by email, it must be printed and scanned before issue so that it cannot be amended by the subcontractor.

Open-format documents or editable exported PDF versions must not be issued where they could be altered by the recipient.

4.15 Scope of Works

Subcontractor Scope of Works documents should be used wherever possible to clearly define:

- The subcontract package

- Inclusions

- Exclusions

- Design responsibility

- Programme requirements

- Health and safety requirements

- Testing and commissioning requirements

- Handover information

- Commercial terms

The appropriate Scope of Works documents should be saved in the project file with the subcontract order.

4.16 Subcontractor Pre-Start Control

Before any bona-fide subcontractor starts on site, the Project Manager / Account Manager must confirm:

- Subcontractor is approved on the Subcontractor H&S Register

- Competence has been verified

- Insurances are valid

- Purchase order or subcontract order has been issued

- Signed subcontract order has been returned where required

- RAMS have been reviewed and approved where applicable

- Pre-start meeting has been completed where required

- Records have been saved in the project file

No subcontractor shall commence works until these controls have been satisfied.

4.17 Invoice and Purchase Order Matching

On receipt of a supplier invoice, the invoice must be matched to the purchase order. The invoice must then be approved by the person who requested or raised the order before it is entered onto the accounts system or processed for payment. Where an invoice is incorrect, disputed, unsupported or does not match the purchase order, it must be queried in accordance with the Commercial & Accounting Procedure using 02-04-35 – Invoice Query Sheet where required.

Where an invoice is incorrect, disputed, unsupported or does not match the purchase order, it must be queried in accordance with the accounts procedure.

5. Compliance / Key Rules

- Official purchase orders must be raised for all purchases

- At least 3 quotations must be obtained wherever practical

- Supplier orders over £25,000 require Director approval

- Bona-fide subcontract orders over £25,000 require Director approval

- Any subcontractor design involvement requires Director approval

- New or unapproved suppliers/subcontractors must not be used without Director approval

- Labour only and bona-fide subcontractors must not be confused

- Bona-fide subcontractors must be approved before use

- Competence must be verified before any subcontractor commences works

- Subcontract orders must be signed and returned before works start where required

- Open-format subcontract orders must not be issued

- Copies of all purchase orders and subcontract orders must be saved in the relevant file

- Invoices must be matched to purchase orders before payment

- All supplier and subcontractor payments must be authorised by a Director in accordance with the Commercial & Accounting Procedure

6. Records / Documentation

- 02-04-20 - Purchasing Sheet

- 02-04-21 - Supplier Quotation Request

- 02-04-19 - Labour Only Subcontractor Timesheet

- 02-04-31a - Subcontractor Purchase Order Form £25,000 to £100,000

- 02-04-31b - Subcontractor Purchase Order Form Over £100,000

- 02-04-32 - Subcontractor Pre-Start Meeting

- 02-04-33 - Subcontractor Tender Enquiry

- Supplier quotations

- Subcontractor quotations

- Purchase orders

- Subcontract orders

- Delivery notes

- Signed subcontractor orders

- Subcontractor Scope of Works documents

- Subcontractor H&S Register

- Project Analysis Sheet

- Project / contract file

7. Monitoring & Review

Purchasing compliance shall be monitored through:

- Project reviews

- Commercial reviews

- Accounts invoice matching

- Subcontractor register checks

- Director approval checks

- Periodic review of purchase orders and subcontract orders

Issues identified during review must be actioned promptly and escalated where required.

The Subcontractor H&S Register shall be reviewed monthly in accordance with the Company Engineers & Subcontractors procedure.

8. References

- Section 3 - Estimating Procedure

- Section 4 - Design & Project Management Procedure

- Section 6 - Commercial & Accounting Procedure

- Section 8 - Training Procedure

- Section 9 - Company Engineers & Subcontractors Procedure

- Subcontractor H&S Register

- COMPANY NAME document control requirements

9. Key Principles

- Purchasing must be controlled before commitment is made

- Cost, quality, programme and risk must all be considered

- Supplier and subcontractor selection must be commercially justified

- Subcontractors must be approved and competent before use

- Records must be complete, accurate and auditable

- Director approval must be obtained where risk, value or non-standard arrangements require it

- No subcontractor should start works until the correct order, approval, competence and safety controls are in place

Start

PURCHASING FLOWCHART

No

Obtain Director Approval to Proceed

Approved Sub-contractor

Obtain Signature From Director

Raise Sub-contract Order on Accounts Software

Issue PO to Sub-contractor

No

Complete Sub-contractor Purchase Order Form IP 02-04-31a For Values In-Between 5k & 100k. For Values Over 100k Use Purchase Order Form IP 02-04-31b

Ensure 45 Day Payment Terms EOM Are Agreed

If Value Over 100k Pre-Start Meeting Must Take Place Using Form IP 02-04-32

Is Sub-contractor Design Involved?

No

Save Sub-contractor PO in File – Only At This Point Can the Sub-contractor Commence Work

Value < £25000

Value > £25000

Obtain 3 x Quotations

Raise Sub-contract Order on Accounts Software

Issue PO to Sub-contractor, Have Copy Signed & Returned