Internal Procedures

Section 6

Commercial, Accounting

This document is uncontrolled when printed. Please refer to Sharepoint for the latest version.

VERSION

DATE

AUTHOR

REVIEWED BY

APPROVED BY

NEXT REVIEW DATE

DATE

AUTHOR

REVIEWED BY

APPROVED BY

NEXT REVIEW DATE

DOCUMENT REF

IP-01-09-01-06-V1

Contents

INTRODUCTION	2

COMMERCIAL	3

COMMERCIAL MANAGEMENT PROCEDURE FLOWCHART	22

CHANGE MANAGEMENT PROCEDURE FLOWCHART	23

LAST SHOT PROTOCOL	24

CASHFLOW OPTIMISATION	26

LETTERS OF INTENT	32

PAYMENT NOTICES & PAYLESS NOTICES	35

BONDS & WARRANTIES	39

ACCOUNTING	45

INTERCOMPANY ACCOUNTING CHECKS	58

CREDIT CONTROL	59

ACCOUNTS DATES TO REMEMBER	62

# INTRODUCTION

Our procedures exist for a reason. They protect our standards, our people and our reputation. At COMPANY NAME, following procedures isn’t about bureaucracy - it’s about delivering quality work with consistency and discipline. It reflects the pride we take in doing the job properly, the responsibility we have to our customers and colleagues and our commitment to continuous improvement.

Clear processes help us manage risk early, communicate effectively and ensure that no detail is overlooked. They create fairness, accountability and a shared way of working across the Group. Most importantly, they allow us to operate safely, professionally and profitably.

Everyone at COMPANY NAME is trusted to apply judgement within the framework we provide but that trust comes with the expectation that procedures are understood, followed and upheld. Doing so protects what makes us strong today and supports our progress for the future.

# COMMERCIAL

1. Purpose

To ensure all commercial activities are followed across all project stages, from pre-contract award through to project completion. It ensures consistency, risk management, financial control, and contractual compliance.

2. Scope

This procedure applies to:

- Commercial Management

- Project Commercial Reporting

- Applications and Invoicing

- Accounting / Financial Management

- Cashflow Forecasting

- Subcontractor Applications and Certification

- Management Reporting

- Variations and Changes

FOR CLARITY Small Works shall be managed in accordance with the company definition contained within Section 4 – DESIGN, PROJECT MANAGEMENT.

3. Responsibilities

Commercial Manager

- Oversee commercial risk and contractual compliance

- Approve contracts, variations, and key commercial decisions

- Liaise with clients on contractual matters

- Ensure financial reporting accuracy

Quantity Surveyor

- Manage day-to-day commercial activities

- Administer contracts, payments, variations, and reporting

- Maintain accurate records and forecasts

Project Managers

- Complete monthly project reports

- Provide accurate commercial updates

- Support subcontractor certification process

- Responsible for project delivery and performance

- Support QS in valuations, procurement, and reporting

Director

- Approve key commercial decisions and risks

- Provide strategic oversight

Accounts Team

- Support payment processing

- Maintain accounting records

- Provide accounting data to commercial team

4. Procedure / Process

NOTE: If any dates clash with a weekend, they must be brought forward to the Friday

4.1 Pre-Contract Award

4.1.1 Client Financial Assessment

- The Commercial Manager shall feed into and assist in the Bid/ No Bid Review stage, updating and populating document Bid, No Bid document 02-04-55 where required.

- The Commercial Manager shall assess the client’s financial standing prior to contract award or handover.

- The following information must be checked against the company credit insurance to determine credit cover;

  - Client information: Company name in which the order is to come via, and company registration number

  - Anticipated contract value

  - Tendered / anticipated duration of the works

  - Understanding of the average, or the highest value peak during the duration of the monthly invoice/ application for payment

- Findings shall be reviewed with a Director and inform tender strategy and contractual protections. i.e. is some form of financial guarantee/ payment security may be required as a condition to the contract.

4.1.2 Commercial Resource Allocation

- A QS must be assigned to each project by the Commercial Manager prior to or upon contract award.

4.1.3 Review of ITT Terms & Conditions

- The Commercial Manager is to review all client terms and conditions.

Note: Where terms and conditions are not contained within the ITT, these are to be requested in the first instance.

- Risks and amendments must be identified using the required Client T&Cs Comments & Risk Analysis document 02-04-42, with the appropriate risk analysis to be undertaken against each item populated for business consideration.

- Key areas include:

  - Payment terms

  - Liability limits

  - Third Party Rights

  - Collateral Warranties

  - Loss Ascertained Damages

  - Cross Contract Set-Off

  - Delay Provisions and Notifications

  - Design responsibility/ liability (i.e. fitness for purpose/ reasonable skill & care)

  - Variation provisions

Note: The above is non-exhaustive only serves to identify high level key areas of review.

- Feedback on the client shall be issued where appropriate and approved by the Director.

4.1.4 Tender Cashflow

- Subject to project; complexity, value, and duration, the QS shall produce a Nett Cashflow Forecast to assess financial impact in terms of cash and revenue.

4.2 Contract Award & Project Set-Up

4.2.1 Handover

- Upon award, a formal handover meeting shall be conducted between estimating team, operations team, and commercial team.

- All commercial actions shall be recorded and actioned by the QS.

- Document 02-04-36 Contract Handover Meeting Minutes is to be used to record all actions from the meeting.

4.2.2 Contract Review and Execution

- To protect the company, upon receipt of a Purchase Order or Sub-Contract Order, the QS is to comply with the companies ‘Last Shot Protocol’ and issue an Order Acknowledgement as per document 02-04-44. Please refer to the Last Shot Protocol as detailed in this document.

Note: this is to ensure that the order aligns and reflects the companies winning bid;

- Value

- Terms and Conditions

- Scope of Works inc Design

- Duration

- Documentation/ Drawings/ Specifications

- The QS and Commercial Manager shall review all contractual documents to ensure alignment with the tender.

- Any discrepancies must be resolved with the client with the utmost urgency.

- Commercial Manager is to liaise with the client’s representative, as appropriate, to negotiate and agree mutually acceptable terms prior to execution of contract.

- Once acceptable and clean copy issued, contracts must be formally executed prior to commencement.

- Final documents shall be securely stored in the project folder in location 04 on SharePoint.

4.2.3 Job Opening

- Either in tandem with the above or prior to such subject to timing, the QS shall initiate the Job Opening Sheet 02-04-01.

- The Job Opening Sheet is to be submitted along with a copy of the contract to adminservices@COMPANY NAME.com

4.2.4 Tender Analysis & Procurement Planning

- The QS and Project Manager shall:

  - Validate cost and sell positions

  - Allocate budgets

  - Produce a Project Analysis Sheet 02-04-02 aligned with the Tender Position

  - Establish a Procurement Tracker 02-05-01-18

Note: the procurement tracker is to fully align itself with the tender analysis document and the allocation of budgets.

- Where the project is to be self-delivered, the QS in conjunction with the Project Manager is to breakout all tendered labour hours.

- Labour Productivity Document 02-04-43 is to be populated for the targeted hours to undertake the works.

- The Labour Productivity document 02-04-43 is to be regularly updated to provide visibility on labour efficiencies and also assist in forecasting the total cost.

- Any risks or opportunities found are to be fed back to the estimation department contracts director, and operations director accordingly.

4.2.5 Powers & Obligations

- The QS shall prepare a Powers & Obligations document 02-04-43 outlining key contractual requirements:

  - Hierarchy of documents

  - Programme – sections for completion, practical completion, damages

  - Payment provisions

  - Design obligations

  - Contractors’ requirements / subcontractors’ proposals

  - Bonds and warranties

  - Change control and delay notifications obligations

  - Contract sum and schedule of rates

  - Post completion and defects obligations

Note: The QS is to show full understanding of key contract requirements as noted above.

- This shall be communicated and presented to all project team members.

4.2.6 Cashflow Strategy

- Upon the request of the Commercial Manager, a project cashflow forecast shall be developed and maintained.

Note: All costs are to align with either Tender Analysis Document, or and Re-validated version subject to the latest and prevalent project situation.

- The QS is to actively manage the project cashflow throughout the project lifecycle.

- The Cashflow Optimisation section of this procedure sets out the considerations that are to be made in the application/ invoicing of monies upstream, and certifications downstream.

4.3 Pre-Construction

4.3.1 Contract Formation

- No works shall commence without a formal contract PO, Sub-Contract Order, or LOI, or without having issued an Order Acknowledgement 02-04-44, unless approved by the Commercial Manager and Director.

- In exceptional circumstances it may be acceptable to commence on a Letter of Intent.  Full details of this can be found in the Letter of Intent section of this document.

- Regardless of the form of contract, the QS must ensure it obtains:

  - Notice to commence and issues the appropriate acknowledgement 02-04-46

  - Agreed start date

  - Defined scope

4.3.2 Procurement

a) Enquiries and Project Analysis

- The QS shall in conjunction with the Project Manager clearly define scope and requirements within all enquiries by using document 02-04-33 Subcontractor Tender Enquiry to supply chains.

- Bids shall be evaluated using Project Analysis Sheet 02-04-20, and benchmarked against the broken-down budget(s), and also each competitive bid received.

- Purpose is to identify and provide a competitive edge between bids, inclusions, and to the betterment and optimisation of margins.

b) Subcontract Placement

- Sub-Contract Order shall be prepared and issued on the below forms, based on value thresholds:

  - £0–£25k: Sub-Contract Purchase Order; At all times noting this does not negate the need to stipulate in the order the; Scope of Works, Commencement & Duration, Drawings, Documentation & Specifications, and Pre-let meeting minutes

  - £25k–£100k: 31a. Sub-Contract Agreement Form 02-04-32a

  - £100k+: 31b. Sub-Contract Agreement Form 02-04-32b

- The QS is to ensure that the details of the discussion are adequately recorded and reflected in Subcontract Pre-Let Meeting Minutes 02-04-32.

- Pre-let meetings must be conducted, documented, and included as a numbered document in all cases above.

- The QS is responsible for preparing the subcontract and all associated documentation.

- Once the Sub-Contract Order is drafted and pre-let held, the QS is to raise the Order on the accounts software and inform the Commercial Manager to seek approval.

- When approved the QS is to PDF the Order and issue.

- The QS is to save the issued email on SharePoint in the relevant/ appropriate project folder in location 04.

- Should a Sub-Contractor contest or amend our standard Sub-Contract Terms and Conditions, the QS is to inform the Commercial Manager in the first instance for them to address.

- The Commercial Assistant is to add the Sub-Contractor and details onto the combined Sub-Contract Tracker 02-04-48 and raise a template CSA for Payment Certifications.

- The QS is to ensure that a signed, unamended copy of the Sub-Contract is received from the Sub-Contractor prior to commencement of the works on site, and/ or prior to the first payment being made.

- The QS is to ensure the signed copy of the Sub-Contract is saved on SharePoint in the relevant and required folder.

c) Internal Group Companies

- Internal COMPANY NAME Group Companies orders, regardless of value - are to be placed via the Sub-Contract Purchase Order.

- The above shall not diminish the requirement for the completing and issuing with the sub-contract order the scope of works, Commencement & Duration, Drawings, Documentation & Specifications, and Pre-let meeting minutes.

- This is to ensure all parties are aligned as to requirements for the works and not to expose the other party to any breach or default under the contract.

- In regard to valuations for Internal Group Companies. These are dealt with via invoices & not applications.

- The project QS shall, prior to the project’s own claim for monies being submitted, liaise with the COMPANY NAME Group Company and gain an advanced copy of their invoice, to factor into the whole project interim claim.

d) Letters of Intent

- Only used in exceptional circumstances and must follow approval procedures.

- The Letter of Intent section of this document must be references.

4.4 Upstream Account Management

4.4.1 Applications for Payment/ Invoicing

- Applications must be submitted strictly in accordance with contract deadlines to the persons/ address noted in the contract.

- All works, preliminaries, variations, and materials (on & off site) must be included.

- Records must be maintained.

- Where Invoices are required to entitlement payment, the QS is to ensure that Invoice Requests 02-01-03 are submitted to accounts on time to ensure that invoices can be issued by the end of the month.

- Applications are to be raised on accounts software with the correct details and dates, and with the correct value claimed against the appropriate lines to generate the claimed value.

- Once complete, the QS is to PDF the summary and schedule of the application for payment from accounts software and submit this to the applicable contractual person or email address, along with any basis and calculation used.

- All invoice requests and submission correspondence are to be saved in the appropriate folder within the project folder on SharePoint.

- Where Applications are the mechanism to claims monies, the QS is to note that any project Final Account Statement signed and issued to the Client is to be applied through Construction Manager to the Final Account Value so that the system does not recognise any undue debt balance on the project.

4.4.2 Payment Certification

- The QS shall:

  - Review client certificates

  - Ensure these are received on time from the client

  - Challenge discrepancies

  - Monitor payment timelines and prompt payments

  - Escalate risks to payment and valuation where necessary

- Prompt payment and the monitoring of this is critical as under our credit insurance policy there are actions that we are required to comply with.

- Extended and/ or repeated defaults in certifications and especially payment will require internal discussion with the Commercial Manager and Directors for considerations as to escalation measures the business may choose to adopt and/ or the exercising of Contractually entitled mechanisms i.e. issuing of Suspension Notices where relevant & applicable etc.

4.4.3 Variations / Change Management

- All changes must be:

  - Properly valued

  - Documented

  - Notified and submitted in line with contract requirements

- No work shall proceed without formal instruction and prior agreement on value.

- Reference is to be made to Change Management Procedure as detailed within this procedure for further guidance.

- Subject to the type and form of contract, the QS shall adhere to the utilising of the following documents;

  - Sub-Contract Form

Where a sub-contract is in place, the QS shall, in the event of the variation, populate the company standard Variation Template 02-04-30, ensuring all details are correct, and once complete and signed off where required, PDF the cover sheet and detailed breakdown page, and submit to the client.

  - Purchase Order Form

Where a purchase order is in place, that contains no mechanism to alter the contracted value, the QS shall in the event of a ‘change’ utilise the formal Quotation Template 02-11-01, ensuring all details are correct etc.

To determine the price of the quotation, the QS shall use the Variation Template 02-04-30, that is the same in nature to the standard variation template, limited to the calculation of the value only.

Note: in the event of a separate PO or the issue of an updated PO, the QS is to then comply with the ‘last shot’ procedure prior to the works being undertaken. This is to occur with every change that is issued under a PO.

- Under no circumstances is the excel to be issued to the client. If requested by the client, the QS is to seek advice from the Commercial Manager.

- Margin that is to be applied in respect to variations and quotations is to be agreed with Directors.

- Submissions are to reference all appropriate documents, drawings, correspondence, etc utilised in determining the scope of the change.

- The QS is to always ensure that all relevant and associated information and correspondence is saved on SharePoint, located in the relevant variation / quotation folder.

4.4.4 Early Warnings

- The QS is to issue all Early Warning Notices as per document 02-04-39 as required by the contract.

- The QS is to ensure that the Early Warning Register on document 02-04-39 is regularly updated and reflective of all those issued.

4.4.5 Claims and Notifications

- Contractual notices must be prepared and issued for:

  - Delays.

  - Disruption

  - Additional costs and expense associated with the above

  - Additional works associated and defined as a variation

- These notices should be regarded as the ‘norm’ rather than the ‘exception’.

- All notices require internal approval prior to issue.

- The QS is to use the Notice of Delay Template 02-04-50 in the required and appropriate event.

- The QS is to ensure that all details and references to contract clauses & conditions are accurate and correct.

- To comply with follow-on requirements of the Delay Notice, the QS is to then prepare for issuing the following templated documents when the details are known;

  - EOT Initial Assessment 02-04-51

  - Loss & Expense Initial Assessment 02-04-52

Note: Notices in relation to Claims and Expense (including follow-on Notices), are to be agreed with Directors, and soft landed with the Client and their team prior to formal submission.

4.4.6 Progressive Account Agreement

- It is imperative that the client is kept fully informed of the likely value of the company’s forecast final account at all stages of the project.

- Regular financial updates must be provided to the client.

- The QS is responsible for project variation accounts, and these must be actively managed and agreed during the lifecycle of the project.

- The QS is to maintain the variation account on the project and ensure all changes, instructed or otherwise, are recorded and captured adequately on Variation Register 02-04-34.

- Where the contract requires, the QS is to ensure that all Early Warning Notices are issued to the Client about changes that occurs in advance of pricing and other associated impacts.

4.5 Downstream Account Management

4.5.1 Subcontractor Management

- The QS shall manage subcontractor accounts, including:

  - Valuations

  - Variations

  - Final accounts

4.5.2 Payment Process

- Sub-Contractors are to submit all Applications for Payment on form

02-04-05.

- All Sub-Contractor Applications for Payment are to be sent to subcontractapplications@COMPANY NAME.com with the QS copied in.

- Upon receipt of a valid application for payment, the Commercial Assistant uploads this onto the account’s software prior to and in anticipation of certification.

- Where there are any claims for variations in the application for payment, the Commercial Assistant is to add such variation lines and total costs to the accounts software to capture the liability.

- The Commercial Assistant will update the sub-contract tracker to reflect the application for payment on the valuation breakdown ready for the QS and PM to value and certify accordingly.

- Applications shall be assessed, certified, and processed in line with contractual and statutory requirements.

- Subcontractor certifications are targeted to be completed by the 12th of the following month, subject to receipt and consideration to our own client certifications where relevant.

- The project QS will be responsible for the following in relation to sub-subcontractor applications for payment:

  - Evaluation

  - Timely preparation and issue of payment and pay-less notices for approval in anticipation of required deadlines

  - Notification (pay-less and/or payment notice) in accordance with the requirements of the sub-subcontract and the Housing Grants Act

- Once the QS and Project Manager have agreed the interim valuation for that application period, the QS or Project Manager is to date and initial in the appropriate columns ready for the Commercial Manager to review and authorise.

- Any deviations from this due to any other issue must be clearly communicated with accounts.

- Once the payment certificate valuation has been fully signed off, the Commercial Assistant is to upload this onto the accounts software to generate the formal payment certificate.

- Once the certificate has been completed the Commercial Assistant is to notify accounts.

- The Commercial Assistant or the QS is to send out the payment certificates (inclusive of the accompanying valuation) no later than 5 days after the due date of each, to the sub-contractor accordingly, and save the relevant issued correspondence on the server.

- The QS is responsible for ensuring this activity is completed and does not leave the company commercially exposed.

- The QS and Commercial Assistant are to be aware at all times of the guidance set out in Payment Notices and Pay Less Notices as detailed in this document.

- Further points to consider are;

- All retentions we are holding need to be checked as per their sub-contract, with only 50% to be released on practical completion.

- When saving certificates and reopening them on the accounts software the dates must be checked at each interval until completed.

- Official purchase orders must be raised for all sub-contractors.

- All final applications must have the Final Account Statement 02-04-16 completed, signed by the sub-contractor & filed before the final payment is made.

- Consideration is to be given to the Cashflow Optimisation section as detailed within this document.

4.6 Financial Reporting

- The Company operates on a strict cycle that is timetabled at the start of each calendar year.

- This timetable is agreed in conjunction between Commercial and Accounts within the first month of the year, if not prior.

- The adherence by all parties as to the deadlines and achieving the dates stated is mandatory to ensure a smooth and seamless reporting period.

- Any delay in in achieving the dates may have a consequential impact on the follow-on reporting by other departments or activities etc.

- Copies of the Commercial Timetable are available upon request.

- The Commercial Manager is to be aware of all requirements and actions to be undertaken on the lead up to and prior to the close of the Financial Year Accounts, with such including but not limited to;

- Liaison with the Management Accountant and review of the PM Commercial Sheets and consolidated Business Unit Reports

- Review and actioning of all Retentions that are due to be Invoiced and Applied for, and paid prior to the end of the Financial Year

- Review of any and all Invoices/ Applications to ensure all projects are up to date and that all relevant Payment Certificates have been received.

- Chasing and ensuring payment of any overdue amounts from Clients

- Final Account Statements both Client and Sub-Contractors are saved in the relevant folder on SharePoint

- Ensuring all Sub-Contractor Payment Certificates are up to date and on Construction Manager, and the Sub-Contract Tracker is updated accordingly

- Any other action or requirement of Accounts as fit and necessary

- It is prudent for the Commercial Manager and Management Accountant to meet and review the above at least every quarter to ensure and minimise any delays or issues to the close of the Financial Year Reports.

4.6.1 Project Analysis Sheet

- Accounts close the costs for the relevant period as per the commercial timetable. This is typically between the 11th – 14th of the current month (subject to weekends).

- Dates for the monthly project commercial reviews will be calendarized in advanced with the invites being issued by the Commercial Assistant to the relevant persons. These are typically between 20th – 25th of the month (subject to weekends).

- Upon cost close accounts advise the commercial team of this to commence the commercial reporting for that period.

- The QS is to produce the Project Analysis Sheet 02-04-02 and liaise as required with the PM to assess programme and resource requirements.

- Monthly reports shall include:

  - Costs to date

  - Forecast costs and value

  - Sales

  - Projected margin

- Whilst the QS is responsible for preparing the project analysis sheet, ultimately it is the Project Manager who is responsible for the commercial performance of the project.

- The Project Manager is to ensure that they are fully aligned with the key assumptions underpinning the forecasts, especially with regards to programme durations and resource requirements.

- The QS and Project Manager will present the project analysis sheet to the Directors and Commercial Manager at the monthly reviews, on the dates calendarized.

- Training and guides as to the project analysis sheet, how to source the information, and data input are available under separate cover.

- The Commercial Manager following the monthly meeting is to take the forecast sales, costs, and margins etc, and complete the Monthly Project Commercial Reports 02-04-13 for each Project Manager for inclusion into the accounts.

- During the review of the Commercial Reports, the Commercial Manager is expected to review and check all aspects of each Commerical Report, ensuring that;

  - Forecast Sales and Costs (incurred, open, and cost to complete) are accurate as to the Finance System & Cost Reports, and reflective of the Project Analysis Reports,

  - All projects are in a strong WIP and Cash Positive Position, having been applied / invoiced on time in the period & that this at least covers the cost of sales & percentage for overhead. Note: where Applications are the mechanism to claim monies there may be a delay in Invoiced value, therefore the Commercial Manager is to take this into account

  - Project Retention is populated where appropriate

  - Final Retention dates are accurate and reflective of when the final retention is due to be claimed

  - Project Completion Dates are correct and reflective of the latest/ forecast Completion Date

  - Check all possible retentions have been applied/ invoiced accordingly

  - Check Left To Invoice and that there is nothing left to claim on completed projects, and that these align with Final Accounts. Any discrepancies are to be reviewed/ investigated, and claimed where required.

  - If there is any remaining profit / turnover on completed projects, review and investigate, releasing or correcting any Forecasts as appropriate

  - All values align correctly on the consolidated Business Unit Report, and that there is no discrepancies between the documents that may be carried through to the next stage of reporting etc.

- Upon completion of the Monthly Project Commercial Reports 02-04-13, the Commercial Manager is to inform accounts and the Director as to the reported positions and any movements (positive and negative) to the reported gross profit position.

4.6.2 Risk and Opportunity Management

- A live risk and opportunity register shall be maintained, using Risk and Opportunity Register 02-04-53.

- Financial impacts must be reflected in forecasts.

4.7 Records Management

- The QS and PM shall maintain comprehensive project records, including:

  - Progress reports

  - Programmes inc drop lines and revisions

  - Marked-up progress Drawings

  - Drawing registers

  - Site records & dairies

  - Handover sheets/ trackers

  - Correspondence

4.8 Insurance Claims

- When an event occurs that is likely to be an Insurance claim, the Commercial Manager is to inform the Insurance Broker.

- The Commercial Manager is to be the key contact for the company in its dealings with the broker and the insurance company when a claim arises as and when necessary.

- The Project Manager is to provide technical or other project documentation in support of any claim the company might have to pursue or defend.

- The Project Manager is to ensure that all relevant documents and records associated are stored in the project folder on SharePoint in location 04 in the appropriate location for ease of access and location.

- The Commercial Manager will liaise with the Project Manager and others, as appropriate, to help ensure the timely production of any information the insurer needs, and to help ensure the company acts in accordance with the requirements of its policies.

4.9 Project Completion

4.9.1 Upstream Final Account

- Project final account is to be collated and submitted with the accompanying Project Final Account Statement 02-04-16, in accordance with contract deadlines.

- Upstream accounts should ideally be agreed swiftly.

- The Director or their delegated person is authorised to sign off the client’s final account statement.

4.9.2 Downstream Final Account

- All sub-contract accounts must be settled in alignment with upstream settlement.

- Agreement of the sub-contractor final account will be confirmed by receipt of a signed Sub-Contractor Final Account Statement 02-04-16.

4.9.3 Contract Close-Out

- Upon achieving practical completion of the project or our works, the QS is to issue a Completion Notice 02-04-54 to the client.

- The QS and Project Manager is to ensure the company is in receipt of a practical completion certificate and certificate of making good defects.

- In any event, the QS is to record in writing the date when completion of the works is achieved.

When projects are complete & all retentions applied and paid, the project is to be marked as complete and shall be formally closed and removed from the monthly commercial report and marked as closed on the account’s software. Furthermore, the contract folder on SharePoint will be moved to completed contracts.

5. Compliance / Key Rules

- Commercial reporting dates must be adhered to.

- All applications and invoicing must be accurate and traceable.

- Completed projects must be closed correctly.

- Commercial reporting must align with management accounts.

- Cashflow forecasting must remain up to date.

6. Records / Documentation

- 02-04-55 - Bid/ No Bid document

- 02-04-42 - Client T&Cs Comments & Risk Analysis

- 02-04-02 – Project Analysis Sheet

- 02-04-53 - Risk & Opportunity Register

- 02-04-43 - Labour Productivity Document

- 02-04-13 – Monthly Project Commercial Report

- 02-04-36 - Contract Handover Meeting Minutes

- 02-04-01 – Job Opening Sheet

- 02-04-02 – Project Analysis Sheet

- 02-04-43 - Labour Productivity Document

- 02-04-44 – Order Acknowledgement

- 02-04-45 - Powers & Obligations Template

- 02-04-46 - Notice to Commence

- 02-04-33 – Sub-Contract Tender Enquiry

- 02-04-20 – Purchasing Sheet

- 02-04-31a – Sub-Contractor Purchase Order

- 02-04-31b – Sub-Contractor Purchase Order

- 02-04-32 – Subcontract Pre-Let Minutes

- 02-04-48 – Sub-Contract Tracker

- 02-04-48 - Sub-Contract Tracker

- 02-04-05 – Sub-Contractor Application for Payment

- 02-04-16 – Sub-Contractor Final Account Statement

- 02-01-03 – Invoice Request

- 02-04-30 – Variation Template

- 02-04-34 – Variation Register

- 02-11-01 - Quotation Template

- 02-04-39 – Early Warning Notice / Register

- 02-04-50 - Notice of Delay

- 02-04-51 - EOT Initial Assessment

- 02-04-52 - Loss & Expense Initial Assessment

- 02-04-22 – Project Final Account Statement

- 02-04-16 – Sub-Contractor Final Account Statement

- 02-04-54 - Completion Notice

- 02-05-01-18 – Procurement Tracker

- 02-04-55 – Bid, No-Bid Document

7. Monitoring & Review

The Commercial Manager shall:

- Review all live commercial reporting monthly

- Monitor project profitability

- Ensure reporting aligns with management accounts

- Escalate risks and issues immediately

8. References

- Section 4 – Design & Project Management

9. Key Principles

- Commercial control must be proactive

- Reporting must be accurate and timely

- Risks must be identified early

- Cashflow management is critical

- All commercial records must be auditable

4.        Upstream Account Management

Applications for Payment / Invoicing

- Applications must be submitted strictly in accordance with contract

- Where invoices are triggers for payment, invoice requests to be raised and submitted to accounts

- Applications to be raised on accounts software

- Application schedule and summary are to be PDF’d and submitted as per the contract

- Copy of issued application or invoice request to be saved on SharePoint

Payment Certification

- Payment certification to be reviewed and challenged where required/ appropriate

- Payment dates are to be monitored to ensure prompt payment

Variations/ Change Management

- All variations to be recorded and notified to the client as per contract requirements

- Variations to be properly valued and submitted in line with contract requirements

- No variation works to proceed without formal agreed instruction

- Variations are to be prepared and submitted on the correct documentation

- Information and records supporting a variation to be saved on SharePoint in the project folder

Early Warnings

- All early warning notices to be issued as required by the contract

- Early warning register to be updated regularly and reflective of all those notices issued

Claims and Notifications

- Notices in regard to delays, disruption, loss & expense etc are to be drafted for review and internal agreement

- All notices require approval prior to issue

- Template to be utilised when applicable

- Notices are to be agreed with Directors and prior to formal submission to the client.

Progressive Account Agreement

- Regular financial and forecast account updates must be provided to the client

- Accounts are to be actively and progressively agreed throughout the course of the works

- Variation/ quotation schedules to be kept up to date

3.        Pre-Construction

- Order [PO/SCO/LOI] must be received and acknowledgement issued

- Prior to commencement, imperative we acquire an agreed start date and a notice to commence, with appropriate confirmation being issued

- Sub-Contractor enquiries to be collated and sent out

- Upon receipt of tender returns, purchasing analysis to be collated for decision and agreement on package

- Sub-contract orders to be drafted

- Sub-contract orders to be raised on Construction Manager

- Commercial Manager to approve sub-contractor on accounts software to enable order number

- Sub-contract order to be issued

- Applications for payment to be issued for all pre-construction & design activities undertaken during this phase

COMMERCIAL MANAGEMENT PROCEDURE FLOWCHART

- Pre-Contract Award

- Assess client’s financial standing

- Allocate commercial resource to the project

- Review of ITT terms & conditions

- Tender cashflow

5.        Downstream Account Management

- All sub-contractor accounts are to be managed in regard to valuation, variations and final accounts

- Applications are to be submitted in COMPANY NAME format to subcontractapplications@COMPANY NAME.com

- Applications to be uploaded onto accounts software with the appropriate lines being added for additional works

- Sub-Contract Tracker to be updated and valuations to be prepared

- Valuation of the applications to be undertaken by the 12th of the following month

- Once valued, Project Manager and Commercial Manager to date and initial sub-contract tracker document

- Valuation to the uploaded to accounts software to generate payment certificate

- Payment certificate to be issued in line with sub-contract requirements

- Final Accounts to be agreed promptly upon completion of the Works

6.        Financial Reporting

- Reporting deadlines and actions are as per the commercial / account timetable for the financial year

- Adherence to the timetable is mandatory

- Copy of the timetable is available upon request

- Upon monthly close off by accounts, the commercial team can complete the project analysis sheets

- Project analysis sheets are to be presented monthly

- Where being self-delivered the labour productivity tracker to be updated in line with the project commercial report

- Risk & opportunity registers are to be kept updated and presented within monthly commercial meeting

- Project Manager monthly commercial reports are to be populated during the monthly commercial meetings and included in the management accounts

- Commercial Manager to inform accounts and Director as to the reported positions and any movements (positive and negative) to the reported gross profit position.

- Contract Award & Project Set-up

- Attend handover meeting between estimation, operations, design

- Review the contract

- Issue PO/SCO/LOI acknowledgement

- Negotiate contract where applicable/ relevant

- Agree contract and execution by Director

- Job opening sheet to be populated and submitted to adminservices@COMPANY NAME.com

- Project analysis sheet to be generated

- Where applicable labour hours to be broken out and analysed

- Labour Productivity Document to be generated & aligned to targets

- Contract Powers & Obligations Template to be prepared and presented to the operations team

- Upon the request of the Commercial Manager, a project cashflow forecast shall be developed and maintained.

02-04-42 - Client T&Cs Comments & Risk Analysis

02-04-02 – Project Analysis Sheet

02-04-53 - Risk & Opportunity Register

02-04-43 - Labour Productivity Document

02-04-13 – Monthly Project Commercial Report

02-04-46 - Notice to Commence

04-04-44 - Order Acknowledgement

02-04-33 – Sub-Contract Tender Enquiry

02-04-20 – Purchasing Sheet

02-04-31a – Sub-Contractor Purchase Order

02-04-31b – Sub-Contractor Purchase Order

02-04-32 – Subcontract Pre-Let Minutes

02-04-48 – Sub-Contract Tracker

02-04-36 - Contract Handover Meeting Minutes

02-04-01 – Job Opening Sheet

02-04-02 – Project Analysis Sheet

02-04-43 - Labour Productivity Document

02-04-44 – Order Acknowledgement

02-04-45 - Powers & Obligations Template

02-04-48 - Sub-Contract Tracker

02-04-05 – Sub-Contractor Application for Payment

02-04-16 – Sub-Contractor Final Account Statement

TEXT IN BLACK DENOTES

RESPONSIBILITY OF QUANTITY SURVEYOR

TEXT IN BLUE DENOTES

RESPONSIBILITY OF COMMERCIAL ASSISTANT

TEXT IN RED DENOTES

RESPONSIBILITY OF COMMERCIAL MANAGER

TEXT IN PURPLE DENOTES

RESPONSIBILITY OF PROJECT MANAGER

9.      Project Completion

Upstream Final Account

- Project final account is to be collated and submitted with project final account statement in accordance with contract deadlines

- Upstream accounts should ideally be agreed swiftly.

- The Director or their delegated person is authorised to sign off the client’s final account statement.

Down Stream Final Account

- All sub-contract accounts must be closed in alignment with upstream settlement

- Agreement of the accounts will be confirmed by receipt of a signed sub-contractor final account statement

Contract Close-Out

- Upon it being deemed we have completed our works, a completion notice is to be issued

- Practical completion certificate is to be received and aligned with issued completion notice

- Expiry of defects liability period, QS / Project Manager to ensure we are in receipt of a making good of defects certificate

- Once projects are complete & all retentions applied and paid, the project is to be marked as complete and shall be formally closed and archived on the monthly commercial report and accounts software.

7.        Records Management

- Comprehensive project records are to be always kept

- Records are to be saved in the project folder in location 04 on SharePoint

- Records are to be kept stored in the appropriate folders to ensure ease of access and location

02-01-03 – Invoice Request

02-04-30 – Variation Template

02-04-34 – Variation Register

02-11-01 - Quotation Template

02-04-39 – Early Warning Notice / Register

02-04-50 - Notice of Delay

02-04-51 - EOT Initial Assessment

02-04-52 - Loss & Expense Initial Assessment

8.      Insurance Claims

- When an event occurs that is likely to be an Insurance claim, the Commercial Manager is to inform the Insurance Broker.

- Commercial Manager is to be the key contact for the company in its dealings with the broker and the insurance company when a claim arises

- Project Manager is to provide technical or other project documentation in support of any claim the company might have to pursue or defend.

- All relevant documents and records associated are stored on SharePoint in the appropriate location for ease of access and location.

02-04-22 – Project Final Account Statement

02-04-16 – Sub-Contractor Final Account Statement

02-04-54 - Completion Notice

5.        Generate the Variation

The greater the detail and breakdown we can provide in the variation, the greater success we will have in recovering the full value of the variation.

The process we should follow when collating the information for the variation is:

- Agree the internal design input costs with the Design Manager (if required)

- Send our enquiries to our suppliers and sub-contractors

- Log all enquiries and response in the variation file from our suppliers and sub-contractors

- Complete the variation template

- Ensure the correct level of prelims have been accounted for

- Ensure the correct level of profit margin has been added to the variation template

- Ensure any agreed discounts/MCD is included

- Update the variation register

CHANGE MANAGEMENT PROCEDURE FLOWCHART

4.        Internal Support Required

Confirmation is required on the level of internal support required – This could be in the form of:

- Design Engineers

- Design Manager

- Estimator

- Ops Manager/Procurement

- Commercial

- Director

The workloads of individual’s should be taken into consideration.

3.        Initial Early Warning Notice

It is the Project Manager responsibility to complete and issue Early Warning Notice.

The proposed change needs to be assessed for the following points:

- Time (this could be increased design, procurement)

- Costs (this could a cost increase, neutral or a saving)

- Resource

- Programme

The above needs to be formally communicated to our client to provide an early warning on the cause and effect of the proposed change.

At this point we can also ascertain if the proposed change constitutes a variation to the contract.

- Logging the Change

One of the most important elements to managing change is the collation of information and record keeping.

The process we should follow when collating the information is:

- Setting up variation folder on the Q file/C file

- Setting up the variation register

- Collating the emails/drawings/information

- Re-confirming verbal conversations back via email

- Proposed Change

A change can be proposed from the following:

- Client

- Architect

- Structural Engineer

- Main contractor / PM / Site

- Design Team Members

The change could be issued in various formats:

- Email

- Upload to a file sharing site

- Verbal

It is the Design Manager/Operations Manager/Project Manager (dependent who has project responsibility) to keep a track of drawing uploads to file sharing sites on a weekly basis.

02-04-34 – Variation Register

02-04-39 – Early Warning Notice

02-04-30 – Variation Template

02-04-34 – Variation Register

9.        Proceed With Change

Upon receipt of the instruction and completion of the items detailed in stage 8, we then complete the following:

- Agree timescales for the required internal design output with the Design Manager (if required)

- Send out new / updated purchase orders to our suppliers and sub-contractors

- Log all purchase orders issued to our suppliers and sub-contractors in the variation file

- Update variation section of the project analysis sheet

- Update the variations register

- Update sub-contractor’s variation log

- Ensure construction manager is fully up to date

8.        Upon Receipt of Instruction

Upon receipt of approval of the variation, we must firstly:

Only accept an instruction from the nominated person detailed within the contract documentation.  Seek advice from the commercial manager if unsure who can approve variations according to the contract. This is also detailed on the ‘Job Opening Sheet’

We then need to complete the following:

- Log the email / instruction in the variation folder

- Confirm back to the nominated person a timeline of events for the design, procurement and installation associated with the variation.

This is important as time may have elapsed between the issue if the variation and approval.

Request the internal support that is required.

7.        Issue VO For Approval

Upon internal approval of the variation the variation can be issued to the appropriate person.

We need to ensure we provide the following:

- COMPANY NAME variation template – in PDF

- COMPANY NAME variation register – in PDF

- Any supporting information – Hand marked drawings, technical data sheets, etc

All information that is issued to the client is to be saved within the variation folder.

6.        Internal Sign Off

If the value of the variation exceeds £10,000.00 or is a risk to the business / completion of the project, then this requires approval prior to issue.

At this stage, consideration is to be given to the level of profit margin being applied to the variation, based on the type, value, programme implications, current project profit margin etc.

02-04-30 – Variation Template

02-04-34 – Variation Register

02-04-02 – Project Analysis Sheet

02-04-34 – Variation Register

## LAST SHOT PROTOCOL

Last Shot Protocol (Battle of the Forms & Order Acknowledgement Requirement)

1. Introduction

This procedure establishes a clear process for managing contractual risk arising from the “battle of the forms.”

It ensures that the organisation’s standard terms and conditions prevail by controlling the exchange of commercial documents and mandating the timely issue of an order acknowledgement.

2. Scope
This procedure applies to all sales transactions where purchase orders, sub-contract orders, quotations, or other contractual documents are received and exchanged with clients.

3. Background (Battle of the Forms)
As is standard in commercial transactions, parties often exchange documents (e.g., quotations, purchase orders, acknowledgements), each containing their own terms and conditions.

Where these terms conflict, the contract is typically governed by the terms contained in the “last shot”—the final set of terms issued and not expressly rejected before performance begins.

Failure to control the “last shot” may result in the organisation being bound by unfavourable counterparty terms.

4. Core Principle
The company must ensure that its terms and conditions are the final terms issued and accepted (expressly or by conduct) before performance, typically through a formal order acknowledgement.

5. Procedure

5.1 Pre-Contract Stage

- All quotations must clearly reference and attach (or link to) COMPANY NAME Terms and Conditions of Sale.

- Quotations must include a statement that any order is subject exclusively to COMPANY NAME Terms and Conditions of Sale.

5.2 Issuing the Order Acknowledgement (Critical Step)

- Upon receipt of a customer purchase order (PO) or a sub-contract Order (SCO), the QS is to prepare the appropriate order acknowledgement and must in all cases be issued before performance begins.

- The order acknowledgement must follow the content contained within the template.

- The order acknowledgement must be sent promptly and recorded.

5.3 No Performance Without Acknowledgement

- Proceeding without issuing the acknowledgement risks acceptance of the counterparty’s terms.

5.4 Counterparty Objection Handling

- If the client objects to the terms in the order acknowledgement:

  - Inform Commercial Manager and Directors immediately for review and consideration on route forward.

5.5 Record Keeping

- Maintain records of:

  - Quotations

  - Purchase orders

  - Order acknowledgements

  - Any correspondence rejecting or negotiating terms

6. Risks of Non-Compliance

- Acceptance of unfavourable customer or supplier terms

- Exposure to increased liability, indemnities, or warranty obligations

- Loss of legal protection intended by standard terms

7. Key Rule (Summary)

Always send the order acknowledgement before performance — whoever fires the “last shot” usually wins.

8. Review and Updates
This procedure should be reviewed periodically to reflect legal developments and business practices.

## CASHFLOW OPTIMISATION

1. Introduction

As well as profitability, our ability as a company to generate healthy, positive cash positions across projects is fundamental to our success.

Within certain constraints and considerations, it is the full team’s responsibility to ensure that we are optimising our projects’ cash position.

Effective pre-planning will help our projects and the company maintain a fair and healthy cash position.

Different projects will offer different options for how we can approach this, but there are some basic steps that should be considered when tendering and delivering projects.

This guide outlines these steps. It is not exhaustive and is intended to be an aide memoire on a project-by-project basis, as not all will be relevant for all projects.

2. TENDERING/ PRE-CONTRACT

Client Credit Score

- Does the client have a good credit score and are we able to utilise this information to negotiate an upfront amount to cover early-stage cash outlays and maintain a healthy cash positive delta.

Credit Cover

- To stay within our credit cover limit, and associated with the project duration, does this likely generate a risk.

- If so, we may be able to negotiate an upfront payment and / or an agreed invoice / draw down schedule / milestone payments.

Understanding the Client and Preferred Valuation / Payment Mechanism

- Is the client familiar with the processes surrounding the Housing Grants Act and contract payment notification constraints?

- It may be advantageous to agree a staged draw down schedule which is invoiced monthly/ milestone payments, with the opportunity to maximise early cash injections and positions etc.

Type of Contract

- Understanding the type of contract we are to be employed under, for example, an NEC4 Option A with activity schedule may present an opportunity to maximise early cash on a broken-down activity basis including the like of ‘first material delivery’, etc.

Negotiating Payment Terms

- Typical and usual nett effect of a healthy cashflow on a project is the payment terms. Notwithstanding all the above, negotiating our payment terms to a maximum 30days from invoice / application for payment is the most recognised.

- This however does not diminish the importance or considerations to the above.

Contract sum build-up

- Consider how we build up the contract sum analysis in terms of how we apportion value and profit.

- We must ensure this apportionment allows us to recover at least our cost on an interim basis.

- It will also be important for the project team to know where the profit sits within the estimate as part of the handover process.

Cash flows for the client

- At times the client may require us to predetermine the cash flow (payments) and will use this for our valuation purposes or sets an expectation in which they will be mindful of.

- We must ensure that any such draw-down schedule allows us to maintain a reasonably positive cash flow from the outset of the project.

Bullet payments

- Consider that as part of our negotiation of terms we might seek early payment on a commercial basis upon execution of the contract.

- Part of this might be justified as upfront mobilisation, but also in consideration of where we expend significant cost and time in bidding or pre-con phase as preferred bidder.

Sensible retention

- Whenever possible, we should resist 5% retention values. On larger value subcontracts, we should push for a 3% limit, as is considered reasonable in the market. Contracts with a retention level higher than 3% must be approved by the Director.

- Where contract values are not significant, are we able to negotiate or agree to Nil Retentions on the basis of value and client’s administration of such etc.

Milestone payments

- These can be a good way to frontload profit or to obtain over measure. As well as presenting this opportunity, however, milestone arrangements can be risky depending on the definition of completion and the degree of subjectivity in the subcontract.

- Avoid definitions that are too rigid or open to abuse.

Supplier payment terms

- Preferential terms with our subcontractors and suppliers will increase our ability to ensure we obtain payment before we have the corresponding outlay.

- Ensuring we agree payment terms to our supply chain that exceed our own (i.e. 45-60day terms), is a beneficial way to generate and maintain a healthy cash position.

Proforma payments

- At times, the purchase of high-value, proprietary products, suppliers may require payment for goods prior to delivery to reduce their commercial exposure and help their cash flow.

- We should back-to-back in this situation, to avoid the company funding such payments. Where possible, we should seek similar arrangement for high-value goods, particularly if we’re able to prefabricate.

- The same provision can be utilised for client nominated suppliers.

Pre-condition clauses

- When negotiating subcontract terms, we should avoid or restrict provisions that enable the main contractor to withhold some or all our payments.

- Typically, such clauses cover provision of ‘as fitted’, O&Ms, warranties and bonds.

3. CONSTRUCTION PHASE

Payment on time

- Receiving payment on time is fundamental to our cash management.

- Although we have a credit control function in the business, it is also a project’s operational and commercial management responsibility to ensure everything is in place for us to obtain payment in good time and to seek payment when it becomes overdue.

- Ultimate accountability at project level for the project’s cash position sits with the Project Manager and QS.

Mid-month valuations

- At times client’s will require our application for payment partway through the month, or even at the mid-month point.

- We will continue to incur costs throughout the full month and so should avoid mid-month valuations.

- Where unavoidable, we must try to ensure that we are entitled to project our works through to the month end for inclusion in the interim payment.

- Such forecasting to month end for works to be undertaken and / or materials to be delivered is a good way to maximise our monthly claims.

Material delivery strategy

- Depending on the payment provisions in the contract, the timing of our material and equipment deliveries will significantly determine the project cash profile.

- Where possible, we should avoid high-value deliveries or large numbers of deliveries shortly after the cut-off date for inclusion in our valuation.

Materials off site

- Seek clear obligation for the main contractor to pay for materials off site and ensure full payment is obtained each month.

- Where necessary, agree vesting terms as early as possible.

Materials on site

- This is typically an area in which main contractors will pay less than our application (on account), rather than properly assess.

- To reduce this risk, we must provide all requisite back-up documentation in good time to ensure full and proper inclusion in our applications and clients’ payment.

Subcontract payment scrutiny

- We should always pay our subcontractors in accordance with the sub-subcontract for the quantity of work or service properly delivered.

- This includes us checking and challenging all applications for payment, as appropriate, to ensure we pay the correct amount.

- It is incumbent on the quantity surveyor to liaise with site management, and to spend sufficient time on site to do so.

Timing of subs’ payment certs

- Our timetable requires that in order to get payments into the system we will often be certifying before we know what level of certification, we are to receive via our contract.

- When setting up projects, consider how we can reduce this potential. We must ensure we obtain payment for at least the same amount of work done as we pay out as the basis of cash management.

- Wherever possible, subcontract payments should be timed for after our final date for payment under our subcontract.

Valuing the works delivered adequately

- We must be paid fairly by our clients for the work or service we provide.

- Properly valuing our account to ensure we obtain payment for no less than the amount of work carried out is essential.

- Given the nature of our contracts, an element of under-certification sometimes occurs, but we must ensure the net over- and under-measure does not equate to less than a fair valuation.

Change control

- Effective change control process will help ensure we identify and value variations in good time.

- We must seek early agreement of all variations to ensure we don’t end up with a growing value in abeyance and to ensure we’re paid the full amount of cash as early as possible after carrying out the work.

- Consider client liaison as part of the project execution plan.

Cost and Margin Mark-up

- Checking the valuation against the project costs to date (and any required forecast to month end) plus project margin (minimum to be set at 10%) ensures that we are able to provide an early benchmark as to whether we are claiming the correct amounts and/ or covering costs in out monthly claims.

Final account close out

- Prompt final accounting with our clients will enable us to obtain earlier final payment (save for retention).

- This should not preclude a proper final account process in full and proper evaluation of our account but will help avoid protracted negotiations and an adverse effect of on the project cash position.

- Key to this will be the effectiveness of our change control process and a ‘day one final account’ approach.

## LETTERS OF INTENT

- Introduction

This document sets out the key points that should be taken into account when the company is considering carrying out work under a letter of intent (LOI) and/ or the employment of our sub-contract supply chain on such.

Ideally and wherever possible, site work or design work is not carried out under a letter of intent. Instead, a formal contract should be executed before work commences.

Notwithstanding the above, the company will carry out works under such an agreement in exceptional circumstances, and only with the approval of a Director.

Letters of intent cover a wide variety of different documents, which can give rise to different legal effects. As a result, it is not possible to give prescriptive guidance regarding acceptable criteria for LOIs. Whether or not a particular LOI is acceptable to the company will be assessed on a case-by-case basis by the Commercial Manager.

Responsibility for the negotiation of the terms of any LOI rests with the Commercial Manager.

- LETTERS OF INTENT FROM CLIENTS

- An LOI in itself is a contract between the parties, albeit usually an abridged version of the full sub-contract.

- It governs the conduct of the parties as a standalone agreement until it is superseded by the subcontract.

- As such, wherever possible, the LOI should meet the following criteria;

  - The letter must not be referenced as being ‘subject to contract’.

  - The letter must include a clear and unambiguous instruction to proceed with the works or a specified part of the works.

  - The scope of the work to be carried out must be clear, as would be the case under the subcontract.

  - The value of the LOI should be clear and a sensible cap defined to avoid the company entering into too long a duration or too extensive a commitment under the LOI.

  - Such value of the LOI must state that this is exclusive of VAT, otherwise this is deemed to include it and lower the expenditure amount.

  - Where a time limit is specified, it must be checked that the financial values are consistent with this.

  - Payment terms must be clear. The letter must state the basis on which payment for the work will be valued and what the arrangements are for interim payments.

  - The letter must refer to the base terms and conditions of the proposed subcontract that are deemed to apply. Where the terms of the subcontract have not been agreed, it is good practice to refer to the unamended form of subcontract where the proposed form is based on COMPANY NAME Standard Terms of Sale.

  - Where possible, the letter should state any exclusions or limitations agreed in respect of the company’s liability (see the tender exclusions for examples).

  - The letter must state a reasonable date for commencement of the work, to allow the necessary lead-in period.

  - The letter should state that no rights are conferred on any third parties.

  - Neither the letter, nor any document enclosed with or referred to in it, should impose upon the company any obligation to enter into, provide or procure guarantees, performance bonds or collateral warranties.

  - The letter must not oblige the company to enter into the formal subcontract until the terms of that contract are agreed between the parties. It is good practice for the negotiation of these terms to be listed as part of the scope of LOI works or services.

  - The letter or the documents enclosed within or referred to in the letter must include appropriate arrangements for termination.

  - Should it be agreed that a sub-contract is not forthcoming or the client is going to others for the works, the remedy clause cites that they are to pay costs incurred plus and agreed % mark-up (such % to be agreed with the Director).

- The letter must be properly executed once agreed and, wherever possible, should include a governing law and jurisdiction clause.

3. LETTERS OF INTENT TO SUPPLY CHAIN

- Where the company is engaged on the basis of a Letter of Intent, any sub-contractor’s that are required to be procured for works under the LOI are to also be procured on the basis of a letter of intent.

- All commercial aspects are aligned, and the company is not at risk should the works not go ahead.

- Downstream letters of intent are to be drafted by the QS using the standard LOI template with the particulars as to the project and works being populated.

- It is essential when drafting a downstream Letter of Intent that;

  - Expenditure Limit: Does not exceed our own limit, even in consideration to any other works that are required to be undertaken.

  - LOI Expiry Date: Aligns with our Upstream LOI.

  - Payment terms: Agreed payment terms that are beyond our own under the upstream LOI.

  - Retention: Minimum 5%

  - Scope of employment under LOI: Detailed scope of works to be provided

  - Insurances: Aligns with our upstream LOI.

  - Agreed package value: If package value agreed then this is to be noted, but clarity to be made this is not the expenditure limit.

  - Documents & specs: Back-to-back our own LOI provisions that we have tendered on.

- Prior to the issue of the Letter of Intent to the Sub-Contractor, the Commercial Manager is to review and approve the drafting of the letter of intent.

## PAYMENT NOTICES & PAYLESS NOTICES

- Introduction

This guide gives a brief overview of what the company needs to do in order to comply with the requirements of contracts and legislation, both upstream and downstream, in relation to payment notices and pay less notices. It also advises of the likely implications of failing to adhere to these requirements.

- What is a Payment Notice

- A payment notice is a document that is required by statute to be issued for every payment made in the construction and engineering sector.

- It is usually issued by the paying party following the receipt of a payment application by the contractor/supply chain, depending on the particulars and the type of contract.

- It is a requirement to issue such notices when paying the subcontract supply chain.

- To fully comply with legislation, the payment notice must include:

  - the amount that the issuer of the notice considers to be due or to have been due at the payment due date in respect of the payment; and

  - the basis on which that amount is calculated.

- Note: it is not sufficient to simply amend the payment against an application for payment without clearly detailing the grounds for doing so and the calculation behind such valuation.

- Legislation

- The underlying legislation that governs the payment procedure and the issuing of payment notices in the UK is The Housing Grants, Construction and Regeneration Act 1996 (HGRA – also known as the Construction Act).

- In summary, this provides for:

  - the right to be paid in interim, periodic or stage payments

  - the right to be informed of the amount due, or any amounts to be withheld

  - the right to suspend performance for non-payment

  - the right to adjudication

  - disallowing pay when paid clauses.

- The Act applies to all contracts for ‘construction operations’ (excluding construction contracts and consultants’ appointments). The scheme for construction contracts applies, should contracts fail to adequately comply with the Act.

- The Act now applies to construction contracts, including those that are not in writing. Adjudication clauses must still be in writing, otherwise the scheme for construction contracts applies.

- The following changes to procedures for making payments have also been made.

- The dates for payments must be clearly included in the contract.

- The payer (or specified person) must issue a payment notice within five days of the date for payment, even if no amount is due. Alternatively, if the contract allows, the payee may make an application for payment, which is treated as if it is the payment notice.

- The payer (or specified person) must issue a pay less notice if they intend to pay less than the amount set out in the payment notice, setting out the basis for its calculation.

- The notified amount is payable by the final date for payment.

- If the payer (or specified person) fails to issue a payment notice, the payee may issue a default payment notice.

- The final date for payment is extended by the period between when the payer should have issued a payment notice and when the payee issued the default payment notice.

- If the payer does not issue a pay less notice, they must pay the amount specified in the default payment notice.

- Pay when certified clauses are no longer permitted and the release of retention cannot be prevented by conditions within another contract. So, for example, contractors on a management contract project must have half of their retention released when their part of the works reaches practical completion, not when the whole project reaches practical completion.

- This also applies to trade contractors on construction management contracts.

- Changes to the right to suspend work for non-payment or to suspend part of the works and to claim costs and expenses incurred and an extension of time resulting from the suspension have also been introduced.

- Issuing a Valid Payment or Pay Less Notice

- In the event of a disagreement over the valuation of the payment in question, the specified person’s failure to issue a valid payment notice within the contractual time limit could result in them being obliged to pay the entire amount applied for as per the contractor’s payment application (which will be deemed a default payment notice).

- The Contractor will be entitled to suspend, adjudicate and/or recover this amount as a debt with interest, should the specified person fail to pay the amount applied for as per the Contractor’s payment application at the final date for payment.

- If the payer disagrees that the amount as per the contractor’s application is due, a pay less notice must be issued within the prescribed period. A notice issued late will be invalid.

- Even if the specified person believes that nothing is due or if they intend to rely on set-off, counterclaim or abatement to reduce or nullify the amount as per the contractor’s application, the specified person must issue a payment notice or pay less notice.

- Having issued the payment notice, if the payer subsequently considers that the payment should be reduced, they have the option to issue a pay less notice to the payee provided they do so in accordance with the terms of the subcontract and sufficient information is provided to ensure the notice is valid.

- This situation would arise where works have been overvalued or contra charges have come to light after the issue of the payment notice.

- If the specified person fails to issue a valid payment notice or pay less notice, they will have no option but to make payment to the contractor for the amount, as per the contractor’s application.

- This is of particular importance at the end of a project, when there is greater potential for account evaluation disagreements or disputes.

- At this point, failure to issue a valid payment notice or pay less notice could result in the paying party having to pay the full amount claimed, whether agreed with or not.

- Once the deadline for issuing a pay less notice in that payment cycle has been missed, the payer has lost the opportunity to withhold money from that payment.

- Not only is it important to issue a valid payment notice or pay less notice within the prescribed timeframe, but the notice must also be in the correct form and contain the relevant details.

- Note: the period between the application date and the due date should be as long as possible, to protect the company’s position in relation to the timing of notices. In addition, the period between the issue of the pay less notice and the final date for payment should be kept as short as possible.

- Conclusion

- In summary, it is important for a valid and timely payment notice or pay less notice to be issued. If it is not, the payee (sub-subcontractor) could be entitled to:

- suspend performance of any or all its obligations under the relevant contract; and/or

- proceed with adjudication to recover what it considers to be the amount due.

- If a case goes to adjudication, the outcome is often in favour if the payee, particularly if the adjudication is brought on the grounds of late notification.

## BONDS & WARRANTIES

- Introduction

This guide covers the procedure to adopt in regard to the use of bonds and warranties.

In the construction and engineering sectors, bonds, collateral warranties and parent company guarantees (PCGs) are commonplace. Bonds and PCGs differ from collateral warranties in that they don’t confer rights to third parties. However, all essentially provide some form of guarantee or recourse over and above that provided under the works contract if a party to a contract defaults in their obligations under the contract or goes out of business.

Typically, during the tendering stage of the project, the client makes us aware of the requirement for a Collateral Warranty, and either a Bond or a Parent Company Guarantee; stating the coverage required (i.e. 10% Performance Bond etc).

Risk profiles are required to be considered for the works, scope, project as a whole, and also the Client when it comes to any agreement to provide or enquire about a Bond or PCG. The critical nature of this is to be emphasised when the type of Bond or PCG are worded in vain of an On-Demand provision.

If the Company is made aware of the requirement of the above then this is to be raised in the first instance to the Director, and Commercial Manager to review and consider the following.

It is Company procedure that the Commercial Manager takes point in regard to any and all requirements for Bonds and Collateral Warranties.

- PERFORMANCE BONDS

A performance bond provides:

  - a guarantee of finance to enable the employer (contractor) to finish the works where the employer would otherwise be financially prejudiced

  - an incentive to the contractor to finish the works

  - a credit assessment of the contractor.

When considering or reviewing a Performance Bond, it is critical to be able to answer the following questions;

- What is the category of the Bond?

Note: There are typically two types of Bonds; On-Demand, or Conditional

- On-Demand Bonds: Relate to breach or non-performance by the contractor, but state that the full amount of the bond is to be paid on first written demand by the beneficiary, without the specific or required need for the breach to be demonstrated or justified in the first instance.

- Considered to be a High Risk. Any commitment to obtain an on-demand bond must be avoided and the situation referred to senior Directors.

- Conditional Bonds: Can only be called upon if a company defaults in its contractual obligations, and that this default or breach requires proof either by; writing of liability by the contractor, or the decision of a court or arbitrator.

This type of Bond is preferred and where always able, negotiated for the wording to be agreed around a Conditional Bond basis, with the limitations set in to the Beneficiary proving breach and defaults etc.

- Bond Duration: Does the wording state the Duration of the Bond and when it is considered to be terminated?

- Should be negotiated that the Bond is to terminate upon Practical Completion of the Works.

- Note: Where no termination date is included, it will remain in force for a long as the Company has any liability under the Contract in which it endures. This is considered High Risk and should never accept or enter a Bond that is open ended.

- What is the Companies current Bonding Capacity?

- This is to be considered by Finance when being sought the costs for the provision of the Bond.

- What are the Calling-In provisions of the Bond? And does this contain a condition precedent?

- ‘calling-in’ of the Bond, to include a condition precedent on the requirement for such claim(s) to be notified within a set period of time from the event giving rise to the claim. This is to enable the bondsman to investigate or avoid a loss, and if there is a delay in notification, the employer/client may lose or reduce any recovery under the bond.

- What is the Cost for the Bond?

- Bonds are considered and are to be treated as a recoverable cost during the Tendering Stage, or by way of a Variation should the requirement come in at a later date etc.

- Upon being made aware of the requirement of a Bond, and informing the Director, and Commercial Manager, the information pertaining to the Bond is to be issued to the Finance Team in order to gain a cost of the Bond.

- Subject to the information received, the Bank or Bondsman may have further queries or requirements to be negotiated with the Client prior to providing a cost or agreeing to cover a Bond.

- In all instances queries and answers are to be fed back to the Client ASAP as to avoid any delay.

- Other aspects to consider and/ or be aware of;

- Bonds are provided based on the Contract in its original and executed form in regards its scope of employment.

- Problems can arise where the original bonded contract has significantly changed because of major variations.

- Where this is the case, the original bond may be void and a new or additional bond will be required.

- Whenever significant changes occur on a bonded contract, the QS is to inform the Commercial Manager in the first instance for them to inform the bank/ bondsman.

- Any costs for the increase in bond due to the increase of the contract value is to be considered and also included in any such Variation as applicable. Even if there is no direct increase, it is prudent to still consider this as the Risk is still a viable factor.

- Subject to the duration of the bond, and also consideration to any value as noted above, it is prudent to consider the increase in cost of a bond in any loss & expense claim the company may have in regard to an extension of time.

- It is the project QS’s responsibility to taken cognisance of the above and ensure that such uplift costs are considered and included in variation / loss & expense submissions.

- Where the above situations become live, the project QS is to inform the Commercial Manager in the first instance.

- PARENT COMPANY GUARANTEES

- Contractors and subcontractors often offer to provide a parent company guarantee (PCG) as an alternative to bond.

- This relieves pressure on bonding capacity and does not require a fee.

- However, this is not a favourable route and to avoid any exposure to risk of the group company, this is not typically an option that should be offered nor considered without any prior agreement with the business senior directorship and the Group CEO.

- COLLATERAL WARRANTIES

What is a collateral warranty?

- A collateral warranty is essentially a contract under which a professional consultant/contractor warrants to a third party (such as a funder) that it has complied with its professional appointment, building contract or subcontract.

- Warranties are typically required from contractors and subcontractors carrying out a design element within their scope. As such, COMPANY NAME is often required to enter into collateral agreements.

- When a collateral warranty is to be provided and the wording of such is contained within the invitation to tender; a copy is to be sent to the Commercial Manager to review and provide any commentary or amendments as required to address or cover the below relevant items;

- Scope of the Warranty: wording to contain Reasonable Skill & Care in associate to the duties. Fitness for Purpose is not to be accepted under any form.

- Compliance: compliance with relevant laws, regulations, British standards etc are to relate back to the contract and not be based on ‘current’. This increases risk exposure.

- Reference: The warranty should always relate back to works done in accordance with the underlying Contract.

- Duration & Expiry: what is the limitation period of the Warranty (i.e. 12years under Deed, or 6 years under simple contract). When does the Warranty start, i.e. Date of Practical Completion, Date of the Warranty itself etc. It is critical that this is not left open-ended.

- Step-in rights: Are there step-in rights allowing the beneficiary (typically a funder) to take over the contract of the employer defaults. Are conditions or notices required to trigger step-in.

- Notice of intent Step-In: Where the provision of suspension and/ or termination of the Contract is included, this is to be set at 7days from Notice should the Employer of the Contract default, and the Beneficiary is in contemplation to Step-In.

- Recovery of monies unpaid: Where possible, and in the even the Beneficiary Steps-in, wording is to be negotiated in that the Beneficiary is to pay to the company any unpaid monies due to the Employer of the Contract’s default.

- Assignability: Can the beneficiary assign the warranty to another party (e.g., purchaser or tenant). Limits on assignability to be set to a maximum of 2no only.

- Limitations on Liability: Ensure there is a limitation of liability included within the Warranty, set to 10% of the contract sum. Ensure consequential loss is excluded.

- Nett Contribution Clauses: are there any which would limit the companies liability to their proportion of responsibility.

- Insurance Levels: Ensure the insurance levels align with that required under the contract, and are that which the company current holds, noting both value and category.

- No Greater Liability Clause: Ensure that there is wording that prevents the Company from being liable under the warranty for more than they are under the original contract. This is important to avoid duplication or expansion of liability.

- Deed vs Simple Contract: Is this warranty executed as a Deed? This affects the enforceability and provide clarity on the limitation period.

- RED FLAGS TO WATCH FOR

- Indemnities: These create higher risk than warranties.

- Uncapped liability: High Risk if no limitation on damages.

- Fit For Purpose: Much stricter than “reasonable skill and care” and not Company accepted.

- Onerous obligations: Ensure you’re not warranting things outside of the company’s control.

- EXECUTION OF BOND AND/ OR COLLATERAL WARRANTY

- Upon the accepted wording of a bond and / or collateral warranty, the Commercial Manager is to request from the client a clean agreed version, which aligns the clauses with all those agreed.

- Once in receipt of the final version, the Commercial Manager is to review a final time and issue to Directors for execution and returning to the client.

# ACCOUNTING

1. Purpose

To ensure all accounting activities are completed accurately, consistently and within required timescales to support financial control and compliance.

2. Scope

This procedure applies to:

- Payroll

- Accounts Processing

- Supplier Payments

- Purchase Ledger

- Nominal Coding

- Management Accounts Support

- Invoice Processing

- Expense Management

- Credit Control Support

3. Responsibilities

Accounts Manager

- Process accounting transactions

- Maintain accounting records

- Complete reconciliations

- Manage payroll administration

- Process supplier payments

- Issue remittances

- Chase outstanding debts and maintain credit control

Commercial Manager

- Provide commercial information for accounting allocation

- Support management accounts preparation

- Confirm subcontractor certification status before month end

Commercial Assistant

- Support the administration of subcontractor applications, payment certificates and commercial records.

- Upload subcontractor applications and associated records onto the accounting software where required.

- Maintain and update the Sub-Contract Tracker in conjunction with the QS and Commercial Manager.

- Notify Accounts when certified subcontractor payment information is complete and ready for processing.

- Ensure subcontractor payment records, certificates and correspondence are saved in the appropriate project folder.

External Accountant / Company Accountant

- Support the preparation and review of company accounts, payroll, PAYE, CIS, VAT and statutory returns where applicable.

- Provide accounting, tax and compliance advice to the Accounts Manager, Group CFO and Directors.

- Confirm PAYE, CIS, VAT and other statutory payment figures in line with required reporting deadlines.

- Support year-end accounts preparation and Companies House / HMRC filing requirements.

- Advise on accounting treatment, tax matters and financial compliance where required.

Health & Safety Manager

- Confirm where subcontractor health and safety documentation, insurance or approval status affects payment approval.

- Notify Accounts and Commercial where a subcontractor is to be placed on stop due to missing, expired or non-compliant documentation.

- Support checks against the Subcontractor H&S Register where required before subcontractor payments are released.

- Confirm when health and safety documentation issues have been resolved so that payment holds can be reviewed.

Directors

- Approve payments

- Review financial information

- Approve credit control escalation where required

Group CFO

- Own the overall financial control framework across the Group

- Review monthly management accounts and key financial reporting outputs

- Review cashflow, funding, intercompany balances and finance facility position

- Approve or review payment controls where required by the delegated authority structure

- Oversee accounting compliance, tax, VAT, PAYE, CIS and statutory filing controls

- Escalate significant financial risks, control failures or overdue reporting issues to Directors / Board

4. Procedure / Process

4.1 Accounting Timescales

NOTE: If any dates clash with a weekend, they must be brought forward to the Friday.

Customer Statements

- On the 1st of the month a copy of all customer statements must be sent out by post.

Payroll Processing

- Timesheets and Expenses are to be added to Payroll Submission form 02-04-56 and sent to the accountants by the Tuesday before the last Friday of the month.

- Once the payroll figures are received back from the accountants no later than the Wednesday, the Accounts Manager will pay all the net figures no later than the Friday.

- A copy of the payslip is uploaded to the payroll portal which all employees have access to.

- All wages paid are to be posted to nominal 2220.

Wage Allocation

- Direct Labour Inc NI costs as received on the 16th of the month by the Commercial Manager will be split into OH & COS, this will be as detailed on the engineer’s breakdown received on the same date also.

- Any costs that are booked to C0000 (Overhead) will go to nominal 7050 & all other Direct Labour Inc NI costs will go to nominal 5001.

Project Cost Reporting

- Each month on or around the 15th of the month, subject to the commercial timetable, the finance department are to issue total project cost information to the Commercial Department via the individual Commercial Report. This data will include; all realised income and costs per project up to and including the last close date which is the end of the Month as per the Timetable.

Monthly Reconciliations

- The bank must be reconciled to the end of the previous month, together with credit card reconciliations completed no later than the 12th of each month.  During the course of the month daily bank reconciliations will also take place to ensure no back log of processing at the end of the month.  As far as possible and no longer than weekly all bank reconciliations are completed for all bank accounts held in the Group.  This ensures ledgers are as up to date as far as possible for mid-month reporting and controls.

- Every customer invoice to be dated the previous month must be on the accounting software, along with all purchase invoices received at this time also.

- Any purchase invoices in query not yet on the accounting software must be dealt with by this point; if these costs are against a contract, then the correct Project Manager must be informed.

- Any supplier invoices or other costs that come in for the previous month past this date must be entered for the next month as it will be past the cut off for the management accounts.

- It is worth checking with the Commercial Manager that all sub-contractor applications have been certified before the accounts are closed off for that month.

Cash Management

In relation to overall project cash management the following key activities take place:

- As part of the monthly Commercial Review Program the PM commercial reports contain data relating to the WIP/Cash position of individual jobs that are reviewed but the Commercial Manager and PM.  If there is any increasing delay on sales application/invoices vs purchase costs realised to the last close date then the Commercial Manager and Project Manager will take action points.

- Bi-weekly the Finance Department will produce and distribute a cash collection report.  This report analyses the individual balance s that are open for collection both as invoice or open unapproved sales applications.  The report is reviewed by the Accounts Manager and Credit Control Manager highlighting balances for escalation to either the Project Manager, Commercial Manager, Director or Group CFO.  The credit control chasing process is a continuous process with this bi-weekly report.

- Every month the Accounts Manager compiles a 13 week cashflow projection that is reviewed by the Group CFO and Group CEO to identify any forecast areas of concern.  In addition the Monthly Group Consolidated accounts also include a YTD cash analysis to highlight any areas of the business that may be absorbing cash unnecessarily.

Nominal Code Checks

- Before the backup of the account’s software is sent a nominal code check will be carried out, this check will determine that only the authorised nominal codes have been used & that the nominal codes on both the accounting software & Construction Manager match.

Accounting Backup

- The Group CFO should consider the back-up services provided by the accounts software that can take into consideration of the software’s cloud infrastructure.  If deemed necessary by the Group CFO a monthly back-up of all data will be downloaded and retained periodically.

PAYE / CIS

- Prior to the 17th of the month the PAYE / CIS combined figure will be received from the Accountant for payment before the 19th of the month.

- Sub-contractor CIS statements are to be sent out by the 18th of the month.

- The accounts team is to complete the CIS return on Construction Manager which is submitted to HMRC. This is then downloaded and sent onto the accountants.

4.2 Accounts Procedures Summary

- Any invoice requests received are to be processed immediately and either emailed or posted in the correct format to the customer straight away.

- Customer credits are only to be raised upon receipt of a credit request form (02-01-11) from either a Director or Project Manager.

- Access to the accounts system should be controlled and approved by the Accounts Manager and Group CFO.

- Subcontractors must be put on stop if the H&S Manager requests so.

- All suppliers must have completed supplier credit control questionnaire (02-01-04) & returned it to us prior to any payments being made.

- All sub-contractors must have completed a copy of the sub-contractor’s questionnaire (02-03-09) & bona fide sub-contractor questionnaire (02-03-56) which is to be approved by the Health & Safety Manager and credit control questionnaire (02-01-04) prior to any payments being made.

- Upon receipt of the mobile phone bill the spreadsheet in folder 06-03 must be updated.

- Official purchase orders must be raised & sent for all purchases made.

- Whenever a payment is made a remittance must be sent out either by post or email in the correct format.

Purchase Invoice Approval

On receipt of a purchase invoice, the invoice should be matched to the purchase order on the system, stapled to it & passed to both the person who requested the order to be raised for the 1st signature & then to a Director for the 2nd signature.

- Only then can it be entered onto the account’s software.

Subcontractor Applications and Payment Processing

- Subcontractor applications and payment certificates shall be controlled jointly by Commercial and Accounts to ensure that applications are properly received, valued, certified, authorised and paid in accordance with the subcontract and statutory payment requirements.

- All subcontractor applications for payment must be submitted to subcontractapplications@COMPANY NAME.com, with the relevant QS copied in where applicable.

- Upon receipt of a subcontractor application, the Commercial Assistant shall upload the application onto the accounting software and record the application on the Sub-Contract Tracker. Where the application includes variations, additional works or claims for additional payment, the Commercial Assistant shall ensure these are recorded clearly so that the potential liability is visible for commercial review.

- The QS, in conjunction with the Project Manager where required, shall review and value the subcontractor application. The review shall confirm:

    - The application relates to an approved subcontract order or purchase order

    - The works, materials or services claimed have been completed or provided

    - The valuation is in line with the subcontract, agreed variations and project records

    - Retention, contra charges, previous payments and other deductions are correctly applied

    - Any disputed values are identified and supported by clear reasons

    - Payment notice or pay less notice requirements are understood and met

- Once the QS and Project Manager have agreed the valuation, the Sub-Contract Tracker shall be updated and initialled / approved in accordance with the commercial approval process. The Commercial Manager shall review and authorise the valuation where required.

- Following commercial approval, the Commercial Assistant shall update the accounting software to generate the formal payment certificate. The payment certificate and supporting valuation breakdown shall be issued to the subcontractor within the required contractual or statutory timescales and saved in the appropriate project folder on SharePoint.

- Accounts shall not process payment until the following information has been completed and made available:

- · Approved subcontract order or purchase order
· Valid subcontractor application for payment
· Commercial valuation / certification
· Payment certificate
· VAT invoice, where required
· Confirmation that subcontractor approval, insurance and compliance status remain acceptable
· Confirmation that any payment hold, dispute, contra charge or pay less notice has been dealt with

- Accounts shall check the payment certificate, invoice, subcontractor account status, bank details and accounting software records before including the payment on the payment run. Any discrepancies, missing records, disputed values or compliance issues must be referred back to Commercial before payment is released.

- Payments shall only be made following approval in accordance with the approved Delegated Financial Authority Matrix. Where no delegated authority is defined, payment authorisation shall default to Director approval.

- The Accounts Team shall process approved payments, issue remittance advice where required and ensure payment records are retained within the accounting software and supporting project records.

- The QS remains responsible for ensuring subcontractor applications are assessed and certified correctly and that the company is not commercially exposed. Accounts remains responsible for ensuring payments are only processed once the required commercial approval, accounting checks and payment authorisation are complete.

- Any deviation from the required process, including late certification, disputed applications, missing records or urgent payment requests, must be clearly communicated between Commercial and Accounts and escalated to the Commercial Manager, Accounts Manager, Group CFO or Director where required.

Payment Authorisation

- All payments are to be authorised by a Director only.

- Only the nominal codes as per 01-09-03 are to be used, no other nominal for the cost of sales & overhead are to be used without prior authorisation.

Bad Debts

Bad debts are to be processed as follows:

- Invoices – credited down to cash amount received, if any insurance monies are received this should be included in the cash amount received & invoiced up to this amount on the project.

- Applications – certified, with full retention release to the amount in cash received, if any insurance monies are received this should be included in the cash amount received & certified up to this amount on the project.

VAT Receipts and Payment Certificates

- As we pay sub-contractors from applications we should have the payment certificates the Commercial Manager sends out signed and returned back to us for VAT purposes, it is up to Accounts to check whether these have been received before making further payments, ideally they are to be signed & returned before the payment is actually made.

Invoice Queries

When invoices are distributed for signing, any queried invoices must be sent to the supplier and adminservices@COMPANY NAME.com explaining the issue and the plan to resolve.

- Admin services will then add details to Invoice Query Sheet 02-04-35.

- If at any stage the query cannot be resolved, and it turns into a dispute it must be passed to a Director to resolve.

4.3 Revenue & Gross Profit Recognition and Work In Progress (WIP)

- Revenue and gross profit shall be recognised on a stage completion basis.

- Stage completion shall be determined by calculating the percentage of total anticipated project costs incurred to date against the latest forecast total cost of the project.

- The percentage completion achieved shall be applied to the forecast gross profit position of the project, with the resulting gross profit recognised through the monthly Work In Progress (WIP) journal process.

- The calculation of stage completion shall utilise the latest approved commercial information available, including project forecasts, anticipated final account values, forecast costs to complete, agreed variations and other relevant commercial information.

- The Commercial Manager and Accounts Manager shall ensure that the most up-to-date commercial reports are utilised in determining the monthly WIP position.

- In certain circumstances, the percentage completion calculation based solely on costs incurred may not accurately reflect the true operational stage of completion of the project. In such cases, an adjustment to the level of profit recognised may be considered.

- Any adjustment to profit recognition outside of the standard percentage completion calculation must be supported by appropriate evidence, investigated fully and approved by the Group CFO prior to processing.

- It is a fundamental principle of the Group that all recognised gross profit is allocated accurately to the individual project and customer to which it relates. No recognised gross profit shall be recorded outside of an identifiable project or customer account.

- As part of the monthly reporting cycle, the WIP balance shall be reviewed to determine:

  - Gross profit recognised to date.

  - Remaining gross profit yet to be recognised.

  - Forecast final gross profit position.

- The recognised and remaining WIP position shall be reconciled to the latest commercial reports and forecasts used by the business. Any material differences between the management accounts and commercial reporting shall be investigated and resolved to ensure alignment between the financial and commercial reporting positions.

- Supporting calculations and records shall be retained to provide a clear audit trail for all WIP and gross profit recognition adjustments.

4.4 Alternative Gross Profit Recognition for High Volume Maintenance and Service Contracts

- Certain areas of the business operate high volume, low value projects and maintenance contracts where the application of individual project percentage completion calculations may not be practical or proportionate.

- In these circumstances, gross profit may be recognised on the basis of actual sales invoices raised and purchase invoices received and processed within the accounting period.

- To ensure that the resulting gross profit position remains materially accurate, a headline review shall be undertaken at the customer, contract or portfolio level to identify any significant sales or purchase transactions relating to works completed but not yet processed within the accounting records.

- Where material unprocessed costs or revenues are identified, an appropriate Work In Progress (WIP) adjustment shall be considered to ensure that the reported gross profit position fairly reflects the underlying performance of the customer account, contract or portfolio.

- The Accounts Manager shall liaise with the relevant Operational Manager, Commercial Manager and Project Manager, where applicable, to determine whether any such adjustments are required.

- Any material adjustments to recognised gross profit arising from this review shall be supported by appropriate information and approved by the Group CFO.

- The objective of this approach is to ensure that gross profit is recognised as accurately as possible whilst maintaining a practical and efficient accounting process for high volume, low value activities.

4.5 Overheads

- Overheads shall be reviewed monthly by the Accounts Manager as part of the management accounts process.

- Appropriate accruals and prepayments shall be processed to ensure costs are recognised within the correct accounting period.

- Material variances shall be investigated and discussed with the individual who approved the expenditure to ensure the nature of the cost is understood and future expenditure can be accurately forecast.

- Significant or unusual overhead costs shall be brought to the attention of the Group CFO where appropriate.

4.6 Management Charges

- Management charges shall be agreed annually by the Senior Leadership Team and reviewed during the course of the year to ensure central costs are being appropriately recovered across the Group.

- The Group CFO shall prepare and present recommendations for management charges to the Senior Leadership Team for approval.

- Management charges shall be processed monthly and recorded accurately within the relevant Group entities.

- Management charges may include, but are not limited to, central accounting, IT, compliance, insurance and other shared support functions.

- Any material variation in central costs shall be reported and, where appropriate, management charges shall be revised or rebates applied to ensure a fair allocation of costs across the Group.

- Intercompany balances arising from management charges shall be reconciled as part of the monthly management accounts process.

4.7 Wages & Salaries

The Finance Department shall produce a monthly headcount and payroll analysis report detailing employee numbers, departmental and entity allocations, total employment costs and relevant KPI metrics, including productivity analysis, with any material movements investigated and reported to the Senior Director of the relevant entity and to Group CFO and Group CEO on a consolidated basis.

4.8 Fixed Assets

The Finance Department shall maintain a fixed asset register, ensure capital expenditure is correctly classified, process monthly depreciation in accordance with Group accounting policies and appropriately account for any asset disposals, impairments or write-offs.

4.9 Trial Balance Reconciliations

As part of the monthly management accounts close process, every balance sheet account on the trial balance shall be reconciled and supported by an appropriate reconciliation, third-party verification or management memorandum. All asset and liability balances must be fully substantiated and reconciled monthly to a standard consistent with the Group's annual statutory audit requirements. The Group's principle is that a month-end close should be performed to the same standard as a year-end close.

4.10 VAT / Sales Tax

VAT returns shall be prepared and submitted in accordance with applicable statutory deadlines. As part of the monthly management accounts close process, VAT balances shall be reconciled to the accounting records, with any material differences investigated and resolved prior to submission. Appropriate records shall be maintained to support all VAT filings and recoveries.

4.11 Payroll Taxes

PAYE, National Insurance, CIS and other payroll-related taxes shall be calculated, reconciled and paid in accordance with statutory requirements and applicable deadlines. The Finance Department shall ensure all payroll tax liabilities are accurately reflected within the accounting records and supported by appropriate reconciliations as part of the monthly management accounts close process.

4.12 Corporation Tax & R&D

Corporation tax and R&D tax positions shall be reviewed regularly by the Finance Department in conjunction with the Group's external advisers. Appropriate records shall be maintained to support all tax filings and claims, with forecast tax liabilities and expected recoveries reflected within management accounts and financial forecasts where appropriate.

4.13 FX

Foreign currency transactions shall be recorded using the prevailing exchange rate at the date of transaction. Foreign currency balances shall be reviewed and revalued periodically, with any resulting exchange gains or losses recognised within the accounting records and management accounts. Any long-term contracts or material foreign currency exposures shall be reported to the Group CFO or Treasury Manager for consideration of appropriate hedging strategies to mitigate foreign exchange risk.

4.14 Consolidation

Consolidated management accounts shall be prepared monthly for the Group. As part of the consolidation process, all intercompany balances, transactions, management charges, sales, purchases and unrealised profits shall be identified and eliminated where appropriate. The Group CFO shall review the consolidated results to ensure they fairly reflect the financial performance and position of the Group.

4.15 Regular Reporting

Weekly Reporting

- Sales/CRM Report

Bi-Weekly Reporting

- Credit Control Report

Monthly Reporting

- Management Accounts

- 13 Week Cashflow Forecast

- Insurance Exposure Report

- Work In Progress (WIP) Exposure Report

- Most Likely Outcome (MLO) Forecast

- Headcount & Payroll Analysis Report

- Consolidated Group Results

Quarterly Reporting

- Quarterly Board Report

Bi-Annual Reporting

- Management Charge Review

Annual Reporting

- Annual Business Plan

- Statutory Accounts

- Corporation Tax Computation

4.16 Banking & Treasury

- Access to banking systems shall be reviewed and approved by the Group CFO and Group CEO.

- All payments shall be subject to dual authorisation in accordance with approved banking mandates.

- Cash balances shall be actively managed by the Group CFO to ensure sufficient liquidity is maintained across the Group.

- Excess cash funds may be placed on deposit by the Group CFO with the approval of the Group CEO.

- Banking facilities, covenant compliance, foreign exchange exposures, hedging arrangements and bonding capacity shall be reviewed periodically by the Group CFO.

5. Compliance / Key Rules

- All accounting dates must be adhered to.

- All payments must be authorised by a Director only.

- Purchase orders must be raised for all purchases.

- Only authorised nominal codes may be used.

- Supplier and subcontractor documentation must be complete before payments are made.

- Records must be complete and auditable.

6. Records / Documentation

- 02-01-11 – Credit Request Form

- 02-01-04 – Supplier Credit Control Questionnaire

- 02-03-09 – Sub-contractor Questionnaire

- 02-04-25 – Sub-contractor Certification Form

- 02-04-05 – Sub-contractor Application Sheet

- 02-04-35 – Invoice Query Sheet

- Engineers Timesheet Spreadsheet – Folder 08-02

- Mobile Phone Bill Spreadsheet – Folder 06-03

- Accounts Software

7. Monitoring & Review

The Accounts Manager shall:

- Ensure monthly reconciliations are completed by the required date.

- Ensure supplier and subcontractor documentation is complete.

- Ensure accounting records are accurate and filed correctly.

- Escalate queries and disputes to Directors where required.

8. References

- Commercial Procedure

- Credit Control Procedure

- Company Financial Procedures

- Construction Manager User Manual

- Xero User Manual

9. Key Principles

- Financial information must be accurate and timely.

- All accounting records must be traceable and auditable.

- Commercial and accounting systems must align.

- Director approval is mandatory for payment controls.

- Accounting information must support cashflow and business control.

## INTERCOMPANY ACCOUNTING CHECKS

1. Purpose

To ensure all intercompany transactions are correctly processed, reconciled and recorded.

2. Procedure / Process

- Prior to the 12th & only after all supplier invoices are on the system, a check is to be carried out to ensure that all intercompany supplier purchases have been invoiced out to the respective group company.

- Prior to the 12th & only after all supplier invoices are on the system, a check is to be carried out to ensure that all invoices for intercompany works completed are on both sides of the relating group company accounting software.

- Once the ledgers are a closed a full check of the intercompany position is required and mandatory monthly to ensure all intercompany transactions are accounted for and balanced:

  - Clear down all intercompany Sales Ledger and Purchase Ledger balances to zero netting off against the intercompany loan account.

  - All intercompany loan accounts must balance.

  - A check is carried out to determine the number of intercompany sales in an individual entity against all other group entities.  That number of sales is journaled out of normal sales into intercompany sales, and the corresponding intercompany purchases are journaled out of the cost-receiving entity from purchases into intercompany purchases.

  - Upon consolidation the following items across all entities must balance to £Nil:

    - Intercompany Sales vs Intercompany COGS

    - Management Charges

    - Intercompany balance sheet balances.

- A check is to be carried out each month to ensure that the intercompany loan position nominal codes match on each group company accounting software.

- This needs to be checked for each company both ways.

3. Key Principles

- Intercompany transactions must be checked monthly.

- Intercompany balances must align across all relevant group companies.

- Errors must be investigated and corrected immediately.

## CREDIT CONTROL

1. Purpose

To ensure customer debt is actively managed and collected in line with agreed payment terms while maintaining good customer relationships.

2. Scope

This procedure applies to:

- Invoices for small works and maintenance

- Applications for contract works

- Customer payment terms

- Debt escalation

- External debt recovery where required

3. Responsibilities

Accounts Manager

- Maintain payment terms records.

- Chase outstanding money as a priority each morning.

- Maintain regular contact with customers.

- Escalate overdue debts in line with this procedure.

- Produce a bi-weekly report on outstand sales invoices and uncertified applications not paid highlighting late payments and where communications are up to including expected payment date and where required escalation progress.

Directors

- Approve escalation to Credit Control Letter 2.

- Approve escalation to legal or external recovery.

- Support customer relationship decisions where required.

4. Procedure / Process

4.1 Payment Terms Control

A record of payment terms must be always kept up to date & accessible.

- For clients that we invoice for small works & maintenance a clear description must be kept of the payment terms on the account’s software under the customers tab.

- For applications on each project on Construction Manager a note explaining the payment terms as per the contract order must be kept.

- If there is a payment schedule for the project, then this is to be attached to the project in Construction Manager.

4.2 Daily Credit Control

- Accounts Manager to chase outstanding money due to be treated as a priority each morning and any time thereafter if agreed with the customer.

- It is preferred that a call or email is made 7 days before each payment is due to confirm amounts being paid are what we are expecting & to ask is the payment being made & are there any issues that need resolving.

- A call should be made on the date of payment to confirm it is being paid.

- If payment is still not received the client should be kept in contact with to find out any reasons why payment has not been made & to request payment at the earliest date.

4.3 Escalation Process

If payment is not received after 7 days, then credit control letter 1 (02-04-27) is to be sent, this can be copied & pasted & sent by email if required.

If payment is not received after 14 days, then approval must be obtained from a Director to issue credit control letter 2 (02-04-28), this can be copied & pasted & sent by email if required.

If payment is still not received after 21 days, then approval must be obtained from a Director to take the debt legal & issue to an external agency to collect.

4.4 Customer Relationship Consideration

In light of the above it is not the company’s intent to be so black & white with credit control procedures, it is important for the company to maintain good customer relationships but also collect monies that are owed.

For example, if a customer is continually late making payments, then the above procedure can be adopted, if a customer is generally good then light phone calls may be more suitable.

It is important for the company credit controller to know the client base, until a credit controller knows the client base then regular contact should be kept with a Director when collecting debts.

5. Compliance / Key Rules

- Payment terms must be recorded and accessible.

- Debt chasing must be proactive.

- Director approval is required before formal escalation beyond Credit Control Letter 1.

- Good customer relationships must be maintained wherever possible.

- Persistent late payment must be escalated appropriately.

- A bi-weekly o/s cash report issued including outstanding invoices and uncertified application and collection progress.

6. Records / Documentation

- 02-04-27 – Credit Control Letter 1

- 02-04-28 – Credit Control Letter 2

- Xero Customer Payment Terms

- Construction Manager Project Payment Terms

- Payment Schedules where applicable

7. Monitoring & Review

The Accounts Manager shall review debtors daily and escalate overdue accounts in accordance with this procedure.

8. Key Principles

- Cash collection must be proactive.

- Customer relationships must be managed carefully.

- Escalation must be proportionate to risk and payment history.

- Director approval is required for formal and legal escalation.

## ACCOUNTS DATES TO REMEMBER

1. Purpose

To maintain visibility of key accounting, tax, VAT, PAYE and CIS dates that must be monitored by the Accounts Manager.

2. Dates

PAYE due/CIS return for December	19-Jan

Personal tax returns filing deadline	31-Jan

Personal tax payments due	31-Jan

PAYE due/CIS return for January	19-Feb

PAYE due/CIS return for February	19-Mar

VAT due date - qtr. ended 28 Feb	07-Apr

PAYE due/CIS return for March	19-Apr

Yearend accounts made up to	30-Apr

PAYE due/CIS return for April	19-May

Annual return due at Companies House	May

PAYE due/CIS return for May	19-Jun

VAT due date - qtr. ended 31 May	07-Jul

PAYE due/CIS return for June	19-Jul

Personal tax 2nd payment on account due	31-Jul

PAYE due/CIS return for July	19-Aug

PAYE due/CIS return for August	19-Sep

VAT due date - qtr. ended 31 Aug	07-Oct

PAYE due/CIS return for September	19-Oct

PAYE due/CIS return for October	19-Nov

PAYE due/CIS return for November	19-Dec

Yearend accounts filing deadline	31-Jan

Corporation tax due date	31-Jan

VAT due date - qtr. ended 31 Nov	07-Jan

3. Key Principles

- Accounting dates must be monitored in advance.

- Payments and filings must be completed by the required deadline.

- Where dates fall on a weekend, actions must be brought forward to the Friday.