## Table 1
Risk Matrix
|  | Project No. | [7 empty] | No Injury/ Damage | Non-reportable Injury/ Damage | Minor Injury / Minor Damage | Major Injury / Major Damage | Fatality / Major Disaster
Project
Schedule
Schedule No.
Revision
|  | Date | [7 empty] | 1 | 2 | 3 | 4 | 5
[8 empty] | Near Certain | 5 | 5 | 10 | 15 | 20 | 25
[8 empty] | Probable | 4 | 4 | 8 | 12 | 16 | 20
[8 empty] | Possible | 3 | 3 | 6 | 9 | 12 | 15
[8 empty] | Unlikely | 2 | 2 | 4 | 6 | 8 | 10
[8 empty] | Remote | 1 | 1 | 2 | 3 | 4 | 5
Ref | Work Stage | Hazards Identified | Person at risk | Risk Level Before Controls (Risk x Probability) |  |  |  | Control Measures | [6 empty] | Risk Level After Controls (Risk x Probability) | bar: 5 4 3 2 1
|  |  |  | Low (0-5) | Medium (6-10) | High (11-15) | Unacceptable (16-25) | [7 empty] | Low (0-5) | Medium (6-10) | High (11-15) | Unacceptable (16-25) | bar: 5 4 3 2 1
Design Risks identified are based on what is outside the expectations/Skill set of a competent Contractor and Maintenance Contractor (i.e. general working at height/working with electricity is not identified). This document is additional to the Construction Risk Assessment.
1 | Installation | Restricted access to existing pump to removed due to existing services and restricted walkways | Contractor |  |  |  | 16(4x4) | Site incumbent "lift and shift" company to be employed to ensure that all measures are taken to remove existing pump and install pump. Site incumbent will know the site and the procedures better than another. To be managed onsite | [7 empty] | 6(3x2)
2 | Installation/Maintenance | New Structural based to be provided in place of existing - base to span over existing floor drain - Base collapse | Contractor/ Maintenance Staff |  | 8 (4x2) |  |  | Full design calculations to be carried out to ensure that the base is strong enough to take the weight of the pump and the span. Calculation to be carried out by Structural engineer to verify. | [6 empty] | 4 (4x1)
Notes
IP 02-05-01-13 Version 1